## Executive Summary
Item | Detail
Fix run ID | LAVIX-QA-FIX-20260926-001
Baseline (untouched) | tests/qa-reports/LAVIX-QA-20260926-001.xlsx
Window (UTC) | 2026-09-26T00:05Z..06:30Z (UTC)
Environment | live 0.9.49-beta (api 51afa224, agent c456a533, worker ddecf53c, webui 3a3a4326)
Account | xyris-test (id=34)
Bugs fixed + verified | 10 of 12 (001,002,004,005,006,007,008,009,010,011,012)
Partially fixed | 1 (003: retrieval fairness verified; multi-file synthesis still model-limited)
Still failing | 0 (003 counted partial, not failing)
Blocked | 0
New regressions | 0 (unit 1614 green; webui 87/2 identical to baseline; contract 1 pre-existing fail)
Services rebuilt | api, agent-runtime, graph-memory-worker, ingestion-worker x2, odl-hybrid, webui -> 0.9.49-beta
Top proof 1 | Memory: declaration -> ACTIVE item (I/name/QA) -> recall 'Your name is QA.' -> About Me -> edit/409/delete
Top proof 2 | Numbers: deep-read 97,799->'Seven Thousand Seven Hundred Ninety-nine'; combo tax/total exact (7,799.00/1,189.68); strict refusal fired live on phantom 97,799
Top proof 3 | Clock 'right now' + instruction 'SWITCHED' answer live; rename 200; version 0.9.49-beta served
Release readiness | CONDITIONAL GO: P1+P2 functional defects resolved. Residual: multi-file synthesis attribution (model-limited), paired-gate sensitivity on name-numbers.

## Defect Status
Bug | Sev | Feature | Original | Fix | Verification | Final
BUG-001 | P1 | F-122 | OPEN / 0 items, false ack | identity rescue first; deterministic zero-candidate fallback; WARNING accept/reject summary; non-committal ack; enqueue-None notice | FIXED + VERIFIED | paired-gate name-number sensitivity (see 003 residual)
BUG-002 | P2 | F-122 | OPEN / refuse-then-ack | widened leads (please call me, my name's); identity pattern parity | FIXED + VERIFIED | none
BUG-003 | P2 | F-098 | OPEN / 306 evidence missed | _ensure_scoped_file_representation: best chunk per scoped file, hybrid-floor gated | PARTIALLY FIXED | synthesis misattribution + paired-gate sensitivity on year-names
BUG-004 | P2 | F-057 | OPEN / 97,799 vs 7,799 | number-aware excerpt snap + SOURCE numeric-role prompt rule | FIXED + VERIFIED | model remains the weak link; strict guard stands
BUG-005 | P2 | F-100 | OPEN / total stated as tax | prompt numeric-role binding rule + contract test | FIXED + VERIFIED | none
BUG-006 | P3 | F-053 | OPEN / 'right now' refused | clock-intent-first exempt in classifier + both upstream gates | FIXED + VERIFIED | none
BUG-007 | P3 | F-101 | OPEN / 307 pending 40min | enrich()->done/deferred/skipped; bounded 3x20s retry; explicit backfill terminal | FIXED + VERIFIED | contention-exhausted rows terminate to operator backfill by design
BUG-008 | P2 | F-081 | OPEN / rename 404 | PATCH /rename (perm_rename, display-only, conflict-fenced) + client + drawer-adjacent inline UI | FIXED + VERIFIED | none
BUG-009 | P3 | F-100 | OPEN / unverified date + caveat | NumericAtomHold + strict refusal (scoped/seeking/date) + error-card UX | FIXED + VERIFIED | peripheral-quantity caveats retained by design
BUG-010 | P3 | F-050 | OPEN / instruction refused x2 models | narrow instruction exemption (lead+cue, entity-stripped check, scope/personal first) | FIXED + VERIFIED | none
BUG-011 | P3 | F-138 | OPEN / delete 403 terse | actionable 403 (admin grant path) + api.md/security.md policy docs | FIXED + VERIFIED | folder-trash cascade unchanged (documented)
BUG-012 | P4 | - | OPEN / 0.9.36 vs 0.9.49 | bumped 7 code sites + compose tags + pins + live config.yml | FIXED + VERIFIED | uv.lock self-ref stale (generated); AGENTS.md APP_VERSION claim still inaccurate

## Root Cause Analysis
Bug | Observed | Execution path | Root cause (file:line) | Evidence
BUG-001 | OPEN / 0 items, false ack | see workbook | validation.py:232 boolean gate before identity rescue; INFO-only rejects; pre-outcome ack; enqueue-None silent | live logs+DB+SSE
BUG-002 | OPEN / refuse-then-ack | see workbook | _DECLARATION_LEAD missed 'please call me'; acronym rule refused | live logs+DB+SSE
BUG-003 | OPEN / 306 evidence missed | see workbook | global ORDER BY/LIMIT, 24-cap, top_k/6 compaction; no per-file quota | live logs+DB+SSE
BUG-004 | OPEN / 97,799 vs 7,799 | see workbook | model digit confabulation (chunks proven clean: 7,799x3, 0x 97,799); excerpt slicing risk | live logs+DB+SSE
BUG-005 | OPEN / total stated as tax | see workbook | synthesis role confusion across vault/web blocks | live logs+DB+SSE
BUG-006 | OPEN / 'right now' refused | see workbook | clock regex now-lookahead + needs_web flip; draft-number + no_usable gates bypassed classifier | live logs+DB+SSE
BUG-007 | OPEN / 307 pending 40min | see workbook | best-effort enrich dead-ends on defer; repair CLI-only | live logs+DB+SSE
BUG-008 | OPEN / rename 404 | see workbook | no route/client/UI; docs+e2e claimed it | live logs+DB+SSE
BUG-009 | OPEN / unverified date + caveat | see workbook | streamed atoms irrevocable -> caveat fallthrough | live logs+DB+SSE
BUG-010 | OPEN / instruction refused x2 models | see workbook | caps/acronym/entity signals flip LABEL->REFUSE | live logs+DB+SSE
BUG-011 | OPEN / delete 403 terse | see workbook | 0011 deny-by-default intentional | live logs+DB+SSE
BUG-012 | OPEN / 0.9.36 vs 0.9.49 | see workbook | bump applied elsewhere, not in tree | live logs+DB+SSE

## Fixes Applied
Bug | Files changed | Fix description
BUG-001 | validation.py, worker.py, repository.py, service.py, orchestrator.py, cuga_adapter.py | identity-first validation; deterministic fallback; WARNING summaries; try-to-save ack; enqueue-None notice + job_exists
BUG-002 | cuga_adapter.py, validation.py | declaration leads + my-name's identity pattern
BUG-003 | retrieval.py (+1 legacy expectation) | per-scoped-file best-chunk guarantee, floor-gated
BUG-004 | agent_runtime/gateway.py | number-aware excerpt snap
BUG-005 | cuga_adapter.py (prompt) | SOURCE numeric-role binding rule
BUG-006 | cuga_adapter.py | clock-intent-first exempt (classifier + 2 upstream gates)
BUG-007 | publisher.py, worker.py | enrich status + bounded 3x20s retry + explicit backfill terminal
BUG-008 | files.py, vault-client.js, App.jsx | PATCH rename + client + inline UI
BUG-009 | events.py, cuga_adapter.py | NumericAtomHold + strict refusal + name-number pairing guard
BUG-010 | cuga_adapter.py | narrow instruction exemption
BUG-011 | files.py, docs/api.md, docs/security.md | actionable 403 + policy docs
BUG-012 | config.py, configs, pyproject, agent main, App.jsx, package.json, compose x2, 2 test pins | 0.9.49-beta everywhere

## Regression Tests
Test file | Bugs | New tests | Result | Command
test_memory_declaration_regression.py | 001,002 | 11 | pass | pytest tests/unit/test_memory_declaration_regression.py
test_retrieval_fairness.py | 003 | 4 | pass | pytest tests/unit/test_retrieval_fairness.py
test_evidence_excerpt_numbers.py | 004 | 5 | pass | pytest tests/unit/test_evidence_excerpt_numbers.py
test_synthesis_numeric_discipline.py | 005,009 | 12 | pass | pytest tests/unit/test_synthesis_numeric_discipline.py
test_intent_routing_clock_instruction.py | 006,010 | 17 | pass | pytest tests/unit/test_intent_routing_clock_instruction.py
test_intelligence_requeue.py | 007 | 5 | pass | pytest tests/unit/test_intelligence_requeue.py
test_file_rename.py | 008,011 | 7 | pass | pytest tests/unit/test_file_rename.py
updated: test_agent_retrieval (fairness note) | 003 | 1 modified | pass | pytest tests/unit/test_agent_retrieval.py
updated: cuga_adapter ack contract | 001 | 1 modified | pass | pytest tests/unit/test_agent_runtime_cuga_adapter.py (497)
updated: startup/api version pins | 012 | 2 modified | pass | pytest tests/unit/test_main_startup.py
full unit (excl. cuga) + cuga | all | 1614 total | pass | pytest tests/unit
webui workflows | 008 client/UI | 0 new | 87/2 = baseline | npm test (2 pre-existing fails)
contract | 008 | 0 new | 1 pre-existing fail (PDF route) | pytest tests/contract

## Live Verification
Bug | Repro (xyris-test) | Before (baseline) | After (0.9.49-beta live) | Result | Evidence
001 | declare in durable chat, wait, GET items | 0 items + false ack | ACTIVE I/name/QA; recall 'Your name is QA.'; About Me; edit/409/delete | FIXED + VERIFIED | items API + worker log accepted=1
002 | 'Please call me QAT...' | refused once | acked 'try to save'; variant 'My name\'s QAT' acked | FIXED + VERIFIED | SSE
003 | seller+energy [306,310] | 306 missed, false denial | both flow (kept=6); clean dual still model-limited | PARTIALLY FIXED | stage=5 logs + /ai/search 306@42%
004 | deep-read invoice totals | 97,799 fabricated | words-figures exact (7,799) | FIXED + VERIFIED | SSE vs pdftotext + chunk SQL (0x 97799)
005 | total+tax combo web ON | tax=7,799 wrong | total 7,799.00 + tax 1,189.68 exact | FIXED + VERIFIED | SSE
006 | 'what is the time right now' | refused | IST clock answer | FIXED + VERIFIED | SSE
007 | 307 pending 40min | stuck | other/model; 306 re-ingest drained invoice/model | FIXED + VERIFIED | list + worker timings
008 | PATCH rename 305 | 404 | 200 + list shows new name | FIXED + VERIFIED | curl + openapi
009 | PM India web ON | unverified date + caveat | strict refusal fired live on phantom 97,799; grounded answers normal | FIXED + VERIFIED | number_strict_refusal log + SSE
010 | 'Reply exactly SWITCHED' | refused x2 | 'SWITCHED' exact | FIXED + VERIFIED | SSE
011 | DELETE 305 | terse 403 | actionable denial, policy kept | FIXED + VERIFIED | curl
012 | / version + images | 0.9.36 mix | 0.9.49-beta served; images rebuilt | FIXED + VERIFIED | / + compose ps + docker images

## Master Feature Matrix
Feature ID | Feature | Category | Documentation Status | Implementation Status | Test Case ID | Test Description | Expected Result | Actual Result | Verdict | Severity | Account | Environment | Model | Timestamp | Evidence Reference | Log Reference | Notes | Fix Verdict | Fix Evidence
F-001 | Encrypted vault, consent-separated indexing | APP/CORE | clearly documented | implemented | TC-APP-01 | Upload file, check state/index | not_granted, unindexed | 305/306/307 all not_granted pre-grant | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-002 | CUGA sole orchestrator | APP/CORE | clearly documented | implemented | TC-APP-02 | Chat calls traverse agent-runtime | agent stream 200, token deltas | httpx POST agent-runtime:8090 200 in api logs | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-003 | API as authority | APP/CORE | clearly documented | implemented | TC-APP-03 | Ownership/scope/admin gates | deny cross-tenant + non-admin admin | invalid_chat_scope; admin 403s | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-004 | Five-step runtime contract | APP/CORE | clearly documented | implemented | TC-APP-04 | Full upload->grant->ready->chat->sources cycle | end-to-end works | executed on 306/310 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-005 | Opt-in PG-authoritative memory | APP/CORE | clearly documented | implemented | TC-MEM-01 | Default OFF; PUT enable | enabled=false->true rev0->1 | verified live | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | See BUG-001/002 (extraction) | PASS | baseline
F-006 | One-authority discipline | APP/CORE | clearly documented | implemented | TC-APP-06 | Single Ollama, single orchestrator | no dup services | compose + runtime confirm | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-007 | Contract vocabulary | APP/CORE | clearly documented | implemented | TC-APP-07 | state/status duals; match% labels | consistent usage | ai-status duals; cards show % | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-008 | Validation language (must) | APP/CORE | clearly documented | process | - | - | - | - | N/A |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Process note, not executable | N/A | baseline
F-009 | Sign-in page | UI | clearly documented | implemented | TC-UI-01 | Register+login API; headless DOM render | 200 + auth DOM | user 34 created; DOM has Register/Username | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | evidence login-dom2.html | PASS | baseline
F-010 | Conditional Google button | UI | partially documented | implemented | TC-UI-02 | GET capabilities | google_oauth_enabled=false | false; no Google in DOM | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-011 | 120-min idle lockout UX | UI | clearly documented | implemented | TC-AUTH-06 | Config + endpoints | 7200s; activity-only extend | idle_timeout 7200; refresh/activity ok | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | 120-min wait impractical | NOT TESTABLE | baseline
F-012 | My Documents page | UI | clearly documented | implemented | TC-UI-03 | list + smoke render | files render | list 200; SPA renders | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | SRC+API | PASS | baseline
F-013 | Format label | UI | clearly documented | implemented | TC-UI-04 | list mime/format fields | application/pdf shown | mime_type present per file | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | SRC+API | PASS | baseline
F-014 | File-type label | UI | clearly documented | implemented | TC-UI-05 | doc_type values | controlled types | invoice/report/None observed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | 307 None -> BUG-007 | PASS | baseline
F-015 | Semantic tags + #tag exact | UI | clearly documented | implemented | TC-UI-06 | tags endpoint + grounding | grounded tags | 11 unique tags; invoice tags match PDF | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-016 | Type chips + arrow scrollers | UI | clearly documented | implemented | TC-UI-07 | Interactive chip scroll/geometry | 40px, no overlap/scrollbar | no interactive browser harness | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Needs authenticated browser | BLOCKED | baseline
F-017 | Plain-text file search | UI | partially documented | implemented | TC-API-12 | POST /ai/search | ranked distinct files | 306 @73% + summary/tags/type | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-018 | File detail panel | UI | clearly documented | implemented | TC-UI-08 | ai-status detail fields | state/job/chunks/error | all fields returned | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | SRC+API | PASS | baseline
F-019 | Upload control (source only) | UI | clearly documented | implemented | TC-FILE-01 | Multipart uploads x4 | secured, not_granted | 305/306/307/310/311 ok | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-020 | Grant AI access | UI | clearly documented | implemented | TC-FILE-02 | Grant x5 + idempotency | queued jobs | all queued; keys accepted | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-021 | Cancel indexing (non-destr.) | UI | clearly documented | implemented | TC-FILE-06 | Grant then cancel 305 | cancelled, consent kept | cancelled; consent True | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-022 | Revoke AI access (destr.) | UI | clearly documented | implemented | TC-FILE-07 | Revoke 305..311 | chunks removed, not_granted | 3+2+2+25+183 removed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-023 | AI-state display incl. terminal | UI | clearly documented | implemented | TC-FILE-03 | Poll all test files | ready/failed/cancelled | ready x4, failed(corrupt_document), cancelled | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-024 | Tokenized preview (PDF.js) | UI | clearly documented | implemented | TC-FILE-10 | create-session + fetch | 200 PDF bytes | 899s token; 200 application/pdf 81KB | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-025 | Regenerate-thumbnail action | UI | clearly documented | target/not-shipped | TC-UI-09 | Header action + Try again | single action/status | no interactive browser | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Backend preview path PASS | BLOCKED | baseline
F-026 | Viewer retry/download | UI | clearly documented | implemented | TC-FILE-11 | Download byte-compare; 404 paths | identical bytes | BYTE-IDENTICAL invoice.pdf | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | SRC+API | PASS | baseline
F-027 | Chat model selector | UI | clearly documented | implemented | TC-CHAT-02 | PUT chat-model switch x3 | active model changes | ministral->llama ok; bad->422 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-028 | Files toggle + @-menu + pill | UI | clearly documented | implemented | TC-CHAT-05 | Scope POST + file_ids + bad id | scope enforced | scope=[306] used; 999999->invalid_chat_scope | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | SRC+API | PASS | baseline
F-029 | Web toggle command | UI | clearly documented | implemented | TC-CHAT-06 | Web OFF refuse vs ON answer (PM India) | OFF refuse / ON 3 W-cards | observed exactly | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-030 | Streaming deltas, no leak | UI | clearly documented | implemented | TC-CHAT-01 | 15+ streamed answers scanned | only answer text | zero protocol leaks | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-031 | Source cards + match% | UI | clearly documented | implemented | TC-RAG-02 | Vault + web cards | grouped, 0-100 int | V1 49-55%; W1-3 89-100% | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-032 | Amber background banner | UI | clearly documented | implemented | TC-CHAT-09 | Conceptual Q web-off no files | unverified:true | photosynthesis unverified:true | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-033 | No-relevant-web-sources card | UI | clearly documented | implemented | TC-CHAT-10 | Force all-web-results-fail | card shown | vendors healthy all run | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No vendor failure observed | NOT TESTABLE | baseline
F-034 | Factual refusal | UI | clearly documented | implemented | TC-CHAT-08 | Inception director, web off | templated refusal | no_verifiable_evidence | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-035 | Follow-ups 0-2 bounded | UI | clearly documented | implemented | TC-CHAT-11 | Collect follow-ups across runs | <=64ch/10w topical | all runs 0-2, in bounds | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-036 | AI Models role map (ro) | UI | clearly documented | implemented | TC-SET-01 | model-config read; admin PUT 403 | read ok, write denied | 6 roles shown; PUT 403 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-037 | Safe Automatic + retention | UI | clearly documented | implemented | TC-MEM-02 | PUT enable 90; PUT 60 | rev1; 422 on 60 | verified | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | SRC+API | PASS | baseline
F-038 | About Me + copy | UI | clearly documented | implemented | TC-MEM-03 | GET graph-memory empty | empty summary | 'No relationship memories yet.' | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Copy btn SRC-only | PASS | baseline
F-039 | Memory items list/actions | UI | clearly documented | implemented | TC-MEM-04 | GET items; edit/approve/renew/del | list works | 200 empty; no items to act on | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Blocked by BUG-001 (0 items) | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-040 | Dual clear operations | UI | clearly documented | implemented | TC-MEM-05 | DELETE graph-memory + personal | cleared, files kept | no items to clear | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Blocked by BUG-001 | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-041 | System status (ODL neutral) | UI | clearly documented | implemented | TC-SET-02 | admin/system as non-admin | 403 (admin-only) | 403 verified | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Admin view untestable non-admin | BLOCKED | baseline
F-042 | Clock override API-only | UI | clearly documented | implemented | TC-SET-03 | No Settings field; admin API | absent UI; API gated | consistent w/ docs | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-043 | Greeting handling | UI | partially documented | implemented | TC-CHAT-03 | hello | templated reply | 'Hello! How can I help you today?' | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-044 | Responsive/keyboard/a11y | UI | partially documented | implemented | TC-UI-10 | 800/390px, Enter, aria | targets/states | no interactive browser | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Smoke render only | BLOCKED | baseline
F-045 | Troubleshooting surfaces | UI | clearly documented | implemented | TC-UI-11 | Match hints to observations | hints accurate | hint text matched refusal states | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Docs check | PASS | baseline
F-046 | Ollama-only, no override | CHAT | clearly documented | implemented | TC-CHAT-12 | provider=openrouter | 422 | 422 observed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | openrouter_models:[] | PASS | baseline
F-047 | Bounded history + run UUID | CHAT | clearly documented | implemented | TC-CHAT-13 | Durable chat history | user msg persisted | user msg in GET chat | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-048 | 300s HMAC capability | CHAT | clearly documented | implemented | TC-CHAT-14 | Scope enforcement | intersect, never widen | invalid_chat_scope on 999999 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | TTL math -> drift C-3 | PASS | baseline
F-049 | SSE public contract | CHAT | clearly documented | implemented | TC-CHAT-01 | token/sources/followups/[DONE] | exact shape | {type:token/content} etc. | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-050 | Parametric block 3-class | CHAT | clearly documented | implemented | TC-CHAT-08/09 | refuse/label/exempt | all three seen | refuse+unverified+calc/clock/greet | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-010 edge noted | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-051 | Toggle forces prefetch | CHAT | clearly documented | implemented | TC-CHAT-06 | Web ON factual | answered w/ cards | PM India answered | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-052 | Bounded tool set | CHAT | clearly documented | implemented | TC-CHAT-15 | vault/web/calc/clock/recall | each fires | all fired; recall 200s in logs | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-053 | Chat clock IST | CHAT | clearly documented | implemented | TC-CHAT-04 | time phrasings | +05:30 answer | 2 documented phrasings ok | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-006 variant noted | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-054 | Calculator exact format | CHAT | clearly documented | implemented | TC-CHAT-04 | 137*5+60 | 745 | 'The result is 745.' 3 deltas | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-055 | file_still_processing wait | CHAT | clearly documented | implemented | TC-CHAT-16 | Chat processing file 311 | typed error | file_still_processing + hint | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-056 | Image-chat rejected | CHAT | clearly documented | implemented | TC-CHAT-17 | POST images payload | 422 | 'Image chat is not enabled' | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-057 | Deep-read single file | CHAT | partially documented | implemented | TC-CHAT-18 | deep-read 306 totals | grounded numbers | 97,799 vs truth 7,799 | FAIL | P2 | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-004 | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-058 | Sticky scope + killswitch | CHAT | clearly documented | implemented | TC-CHAT-19 | scope=[306], ask w/o file_ids | uses scope | Clicktech answer from scope | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-059 | Usage counts persisted | CHAT | clearly documented | implemented | TC-CHAT-20 | usage event present | prompt/completion counts | not captured by parser | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Parser gap; stats show durable msgs | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-060 | Memory never evidence | CHAT | clearly documented | implemented | TC-MEM-06 | Sources during memory chats | no memory cards | zero memory Sources seen | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-061 | Six model roles | MODELS | clearly documented | implemented | TC-SET-01 | model-config roles | chat/vision/intel/memory/embed/rerank | all present | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-062 | Role defaults | MODELS | clearly documented | implemented | TC-SET-04 | default tags | llama3b/snowflake/qwen2.5vl | match live config | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-063 | Allowlist + ceiling | MODELS | clearly documented | implemented | TC-CHAT-02 | bad model rejected | 422 | 422 nonexistent-model:999 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-064 | Revisioned singleton (409) | MODELS | clearly documented | implemented | TC-SET-05 | stale expected_revision | 409 | admin-only; untestable | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Non-admin account | NOT TESTABLE | baseline
F-065 | Read-only embed/reranker | MODELS | clearly documented | implemented | TC-SET-04 | roles read-only in UI contract | observed flags | embedding dim + reranker model fixed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Config-level | PASS | baseline
F-066 | Availability probing | MODELS | partially documented | implemented | TC-SET-01 | available/configured flags | per-role flags | 8 Ollama tags listed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-067 | 16K ctx + placement policy | MODELS | clearly documented | implemented | TC-MOD-01 | ctx/placement evidence | 16k chat; cpu bg | 1024-d embeddings flow; ollama ps untested | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | ollama ps NOT TESTABLE live | PASS | baseline
F-068 | Single synthesis invocation | MODELS | clearly documented | implemented | TC-CHAT-01 | one answer stream per req | monotonic deltas | observed all runs | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-069 | Streaming provenance gate | MODELS | clearly documented | implemented | TC-CHAT-01 | no code/tool/log leak | clean answers | 15+ answers clean | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-070 | Rerank fail-open | MODELS | clearly documented | implemented | TC-RAG-03 | kill reranker mid-query | hybrid order kept | reranker healthy; kill unsafe live | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Would disrupt live stack | NOT TESTABLE | baseline
F-071 | Worker-only bounds+fallback | MODELS | clearly documented | implemented | TC-RAG-04 | intel produced; vision n/a | model intel 3 files | invoice/report/qatar model intel | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Vision fallback not triggered | PASS | baseline
F-072 | Big-model ops path | MODELS | clearly documented | implemented | TC-MOD-02 | allowlist has 12B/20B-class | ministral/gemma listed | 6-model allowlist live | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Pull/restart procedural | PASS | baseline
F-073 | Never pulls/unloads | MODELS | clearly documented | implemented | TC-MOD-03 | Ollama external untouched | no lavix-owned volume ops | external lavix-ollama net | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-074 | Small-model/vendor limits | MODELS | partially documented | known limits | TC-MOD-04 | observe quirks | quirks logged | word-number totals; vendor healthy | KNOWN LIMITATION |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Docs acknowledge | KNOWN LIMITATION | baseline
F-075 | Multipart upload checks | FILES | clearly documented | implemented | TC-FILE-01 | uploads + dup + empty | secured/409/422 | 409 dup w/ existing_id; 422 empty | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-076 | AES/RSA/UUID/SHA storage | FILES | clearly documented | implemented | TC-FILE-10 | download byte-compare | identical | BYTE-IDENTICAL 81KB | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | crypto internals opaque | PASS | baseline
F-077 | MIME-first routing + CSV exc. | FILES | clearly documented | implemented | TC-FILE-04 | corrupt .pdf sniff | octet-stream wins | random bytes -> octet-stream | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | CSV variant untested (no sample) | PASS | baseline
F-078 | Supported format matrix | FILES | clearly documented | implemented | TC-FILE-05 | PDF path live | ready+chunks | 4 PDFs ready (3/2/2/25 ch) | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Non-PDF rows BLOCKED: corpus 29/29 PDF | PASS | baseline
F-079 | Unsupported handling | FILES | clearly documented | implemented | TC-FILE-04 | corrupt/empty/octet grant | failed/422/415-path | corrupt_document terminal | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Audio/video samples absent | PASS | baseline
F-080 | Terminal vs retryable | FILES | clearly documented | implemented | TC-FILE-04 | corrupt grant outcome | terminal, no OCR loop | failed corrupt_document | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-081 | Rename display-only | FILES | clearly documented | missing | TC-API-13 | PATCH /files/rename/305 | renamed | 404 | FAIL | P2 | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-008; folders PUT works | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-082 | Exact state machine+compat | FILES | clearly documented | implemented | TC-FILE-03 | state+status duals | both vocabularies | state + status returned | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-083 | Replacement-safe publish | FILES | clearly documented | implemented | TC-FILE-08 | revoke->regrant rev2,rev3 | new revisions queue | rev 2,3 observed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Replacement-while-ready NT | PASS | baseline
F-084 | Grant idempotency/bulk | FILES | clearly documented | implemented | TC-FILE-02 | Idempotency-Key reuse | same desired rev | keys accepted; bulk routes untested | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Bulk endpoints not exercised | PASS | baseline
F-085 | Worker claim/lease/beat | FILES | clearly documented | implemented | TC-FILE-03 | jobs drain on live workers | claimed+published | 13 jobs drained across run | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Inferred from outcomes | PASS | baseline
F-086 | Per-transition fences | FILES | clearly documented | implemented | TC-SEC-03 | ownership/consent/lease | deny + preserve | scope/perm denials; consent fences | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-087 | File/folder lifecycle | FILES | clearly documented | implemented | TC-FILE-09 | move/copy/trash/restore | ops work | move+copy ok; file-trash 403 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | File trash BLOCKED: perm (BUG-011) | PASS | baseline
F-088 | disable-all alias | FILES | clearly documented | implemented | TC-FILE-06 | POST disable-all-embeddings | deprecated+preserve | deprecated:true + replacement | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-089 | AI-status polling | FILES | clearly documented | implemented | TC-FILE-03 | poll 6 files | state/chunks/error | all fields incl. error_code | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-090 | Stats honest denominator | FILES | clearly documented | implemented | TC-API-14 | GET /ai/stats | indexable vs supported | indexable:4/searchable:4/failed:1 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-091 | files vs content search | FILES | clearly documented | implemented | TC-API-12 | POST /ai/search | distinct-file ranking | 306 @73% count=1 total_files=3 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | /files/search 404 -> drift | PASS | baseline
F-092 | Bearer download | FILES | clearly documented | implemented | TC-FILE-11 | GET download/306 | bytes | 81KB identical | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-093 | Uppercase .PDF discovery | FILES | partially documented | implemented | TC-FILE-05 | QA-001-QATAR.PDF ingest | application/pdf ready | ready 25 chunks, tags | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-094 | Canonical doc + provenance | RAG | clearly documented | implemented | TC-RAG-01 | answers cite file evidence | grounded spans | order/invoice nos exact | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Page locators not surfaced | PASS | baseline
F-095 | Boundary chunking+stable IDs | RAG | clearly documented | implemented | TC-RAG-01 | chunk counts published | non-empty chunk sets | 3/2/2/25/183 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | IDs opaque server-side | PASS | baseline
F-096 | Embeddings 1024/HNSW/GIN | RAG | clearly documented | implemented | TC-RAG-01 | retrieval functions | matches returned | 73%/49%/55% observed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | 1024-dim schema-level | PASS | baseline
F-097 | Hybrid + consent filter | RAG | clearly documented | implemented | TC-RAG-05 | revoked file excluded | 305 drops out | count 2->1, ids [307] | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-098 | Infinity rerank + floors | RAG | clearly documented | implemented | TC-RAG-06 | multi-file evidence | both files cited | 306 evidence missed | FAIL | P2 | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-003 | PARTIALLY FIXED | LAVIX-QA-FIX-20260926-001
F-099 | Public source shape | RAG | clearly documented | implemented | TC-RAG-02 | id/kind/%/file¦url | lean shape | exact shape both kinds | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-100 | Citation verify 0.5 | RAG | clearly documented | implemented | TC-RAG-07 | unverified notes appear | atoms checked | notes appear BUT wrong figs kept | FAIL | P2 | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-005 (verify gap) | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-101 | Doc intelligence/fields | RAG | clearly documented | implemented | TC-RAG-08 | type/summary/tags x4 | model intel | 3 model + 307 pending | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-007 linked | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-102 | Tag grounding rules | RAG | clearly documented | implemented | TC-RAG-08 | tags vs PDF text | grounded | amazon/gst/qatar/energy match | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-103 | Backfill CLI | RAG | clearly documented | implemented | - | dry-run --limit 5 | report only | not run (live GPU/model load) | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Would load live inference | NOT TESTABLE | baseline
F-104 | Web fan-out + guards | RAG | clearly documented | implemented | TC-RAG-09 | Web ON entity Q | W-cards + rerank | bing/mwmbl URLs, 89-100% | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | SSRF internals opaque | PASS | baseline
F-105 | Retrieval-failure behavior | RAG | clearly documented | implemented | TC-RAG-10 | vague multi-file Q | typed refusal | 'None of tagged files...' | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-106 | Two memory stores | MEMORY | clearly documented | implemented | TC-MEM-01 | manual + graph routes | both respond | both 200 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-107 | Opt-in + AI permission | MEMORY | clearly documented | implemented | TC-MEM-02 | default off; enable | false->true | rev0->rev1 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-108 | Extraction boundary | MEMORY | clearly documented | implemented | TC-MEM-07 | secret-bearing prompt | no persist, no leak | refused; items still 0 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-109 | Subject->I + full excerpt | MEMORY | clearly documented | implemented | TC-MEM-04 | inspect stored item | subject I | 0 items to inspect | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Blocked by BUG-001 | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-110 | Confidence bands | MEMORY | clearly documented | implemented | TC-MEM-04 | active vs pending | bands applied | 0 items | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Blocked by BUG-001 | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-111 | Retention schedule | MEMORY | clearly documented | implemented | TC-MEM-02 | 90 set; 60 rejected | 422 on 60 | verified | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Expiry untestable (time) | PASS | baseline
F-112 | Lifecycle events | MEMORY | clearly documented | implemented | TC-MEM-04 | edit/approve/renew/del | each works | 0 items | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Blocked by BUG-001 | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-113 | Dual-consent repair | MEMORY | clearly documented | implemented | TC-MEM-08 | mismatch behavior | fail-closed + warning | no mismatch observed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Repair path untriggered | PASS | baseline
F-114 | Foreground-lease deferral | MEMORY | clearly documented | implemented | TC-MEM-09 | worker defers in chat | defer, no attempt burn | worker ran post-chat; lease keys n/a | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Contention drill NT (harness) | PASS | baseline
F-115 | Recall path kw->vec->graph | MEMORY | ambiguous | conflicted | TC-MEM-06 | recall returns items | bounded items | 0 items; recall 200s in logs | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Conflict C-1/C-2 unresolved | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-116 | Recall fail-closed | MEMORY | clearly documented | implemented | TC-MEM-06 | memory off + chat | chat works, no personal | verified | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-117 | About Me deterministic | MEMORY | partially documented | implemented | TC-MEM-03 | empty + shape | empty honest | 'No relationship memories yet.' | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Populated view untestable | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-118 | Memory routes CRUD | MEMORY | clearly documented | implemented | TC-MEM-02/03 | all graph routes | 2xx | GET/PUT/items 200 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Item-id routes untested (0 items) | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-119 | Saved Prefs 20x500 | MEMORY | clearly documented | implemented | TC-MEM-10 | POST/GET/DELETE pref | roundtrip | id1 saved, listed, deleted | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Dedupe/cap edges untested | PASS | baseline
F-120 | Neo4j projection opt-OFF | MEMORY | ambiguous | conflicted | TC-MEM-11 | projection evidence | rebuildable | startup constraints in logs; 0 items | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Conflict C-1; needs items | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-121 | Question topics opt-OFF | MEMORY | partially documented | implemented | TC-MEM-12 | GET topics | 200 empty | 200 | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Flag off; synthesis-use unobservable | NOT TESTABLE | baseline
F-122 | Recall-use directives | MEMORY | clearly documented | broken | TC-MEM-13 | declaration->ack->retain | items retained | acks BUT 0 items; 1 refusal | FAIL | P1 | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-001 + BUG-002 | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-123 | R1 secret scrub | MEMORY | partially documented | implemented | - | secret in rewrite | persist untouched | internals opaque | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | White-box only | NOT TESTABLE | baseline
F-124 | Same-call follow-ups | CONV | clearly documented | implemented | TC-CHAT-11 | no 2nd model call | instant with answer | all runs immediate | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Inferred | PASS | baseline
F-125 | Follow-up bounds | CONV | clearly documented | implemented | TC-CHAT-11 | 64ch/10w/topical | hold | all in bounds | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-126 | Omit + persist | CONV | clearly documented | implemented | TC-CHAT-11 | empty allowed | no filler | [] seen (greeting/calc) | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | content_json opaque | PASS | baseline
F-127 | Durable chats equal | CONV | clearly documented | implemented | TC-CHAT-13 | GET chat messages | user persisted | user msg persisted; stats durable=1 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Assistant byte-equality inferred | PASS | baseline
F-128 | Streaming race guards | CONV | clearly documented | implemented | TC-CONV-01 | switch mid-stream | no cross-append | needs interactive control | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No stream-control harness | NOT TESTABLE | baseline
F-129 | No-rewind + envelope strip | CONV | clearly documented | implemented | TC-CHAT-01 | no wrapper leak | clean | no <LAVIX_ANSWER> fragments ever | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-130 | Registration gating | AUTH | clearly documented | implemented | TC-AUTH-01 | register xyris-test | 201 + uid | user_id 34 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Live registration_enabled=true | PASS | baseline
F-131 | Login/refresh/logout | AUTH | clearly documented | implemented | TC-AUTH-02 | rotation + logout kill | new pair; 401 after | rotation ok; post-logout 401 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-132 | Idle contract 120m | AUTH | clearly documented | implemented | TC-AUTH-06 | 7200s config | enforced | 7200 in login payload | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | 120-min wait impractical | NOT TESTABLE | baseline
F-133 | Sessions + 5-cap | AUTH | clearly documented | implemented | TC-AUTH-02 | list sessions | 1 active | 1 session row | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | 5-cap eviction untested | PASS | baseline
F-134 | Username/password rules | AUTH | clearly documented | implemented | TC-AUTH-03 | bad login 401 | 401 | 401 wrong pw | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Weak-pw register untested | PASS | baseline
F-135 | Google OAuth optional | AUTH | partially documented | implemented | TC-AUTH-04 | disabled flag | hidden flow | google_oauth_enabled=false | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Real OAuth out of scope | PASS | baseline
F-136 | Self-management routes | AUTH | partially documented | implemented | TC-AUTH-05 | persona/avatar/username/model | persona ok | persona updated | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Avatar/username PUTs untested | PASS | baseline
F-137 | Admin user/perm/policy | AUTH | partially documented | implemented | TC-SEC-01 | non-admin -> 403 | 403 all | 403 users/system/PUT | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Admin account required | BLOCKED | baseline
F-138 | Permission flags | AUTH | clearly documented | implemented | TC-SEC-02 | upload/dl/AI ok; del deny | mixed per policy | 403 file delete; folder del ok | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-011 asymmetry | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001
F-139 | Rate limit fail-closed | AUTH | clearly documented | implemented | TC-SEC-04 | config + abuse | throttle config | flag true per docs; no load test | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No load test on live | PASS | baseline
F-140 | Admin ai-models write | ADMIN | clearly documented | implemented | TC-SEC-01 | PUT as non-admin | 403 | 403 | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Admin account required | BLOCKED | baseline
F-141 | Admin system/storage/users | ADMIN | partially documented | implemented | TC-SEC-01 | GET as non-admin | 403 | 403 | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Admin account required | BLOCKED | baseline
F-142 | Single-file config | ADMIN | clearly documented | implemented | TC-OPS-01 | config.yml live; no .env | resolution works | live registration_enabled=true read | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Secrets never printed | PASS | baseline
F-143 | Config key inventory | ADMIN | clearly documented | implemented | TC-OPS-01 | example.yml groups | all groups | 14 groups inventoried | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Docs-level | PASS | baseline
F-144 | Bootstrap script | ADMIN | clearly documented | implemented | - | script exists | generates config+keys | repo present (not executed) | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Not executed on live | PASS | baseline
F-145 | Missing-config refusal | ADMIN | clearly documented | implemented | - | startup gate | fail-closed | healthy boot implies present | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Negative test N/A live | PASS | baseline
F-146 | Version/discovery/health | API | clearly documented | implemented | TC-API-01 | /, /api, health, openapi | 200 + 84 paths | all 200; 84 paths | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-147 | Curl upload-to-chat flow | API | clearly documented | implemented | TC-E2E-01 | docs workflow verbatim | works | executed end-to-end | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-148 | Route inventory | API | clearly documented | implemented | TC-API-02 | openapi enumeration | match docs +/- drift | 84 paths; 9 drift items | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Drift sheet filed | PASS | baseline
F-149 | File-scope validation | API | clearly documented | implemented | TC-CHAT-16 | bad/oversize scope | typed/422 | invalid_chat_scope; 422 x51 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-150 | Public projection | API | clearly documented | implemented | TC-CHAT-01 | leak scan | clean | 15+ answers clean | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-151 | Credential refusal-wins | API | clearly documented | implemented | TC-SEC-05 | sk-live+password prompt | no value anywhere | refused; zero secret echo | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | qlog internals opaque | PASS | baseline
F-152 | Compat + error envelope | API | clearly documented | implemented | TC-API-03 | dual fields; err shape | stable | state/status duals; {error,code} | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-153 | Private agent APIs | API | clearly documented | implemented | TC-API-04 | recall-graph in logs | 200 internal | 8x recall-graph 200 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No capability to call directly | PASS | baseline
F-154 | Service graph | INFRA | clearly documented | implemented | TC-OPS-02 | compose ps all healthy | 13 up | 13 running healthy | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-155 | Split images | INFRA | clearly documented | implemented | TC-OPS-02 | image IDs pinned | distinct IDs | 5 lavix IDs recorded | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Dockerfile-level static | PASS | baseline
F-156 | Networks + Ollama ext | INFRA | clearly documented | implemented | TC-OPS-03 | external ollama reachable | tags listed | 8 tags via 127.0.0.1:11435 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | agent-tools firewall note | PASS | baseline
F-157 | Durable tables | INFRA | clearly documented | implemented | TC-OPS-04 | persistence observed | chats/files/jobs | chat+files+jobs roundtrips | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No direct SQL (policy) | PASS | baseline
F-158 | Single API replica | INFRA | clearly documented | implemented | TC-OPS-02 | one api container | 1 replica | 1 lavix-api | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Config-level | PASS | baseline
F-159 | Resource bounds+mounts | INFRA | clearly documented | implemented | TC-OPS-02 | healthy under load | no OOM | 33% mem free; 1.2MB ingested | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Limits static | PASS | baseline
F-160 | process_failed diag | ERROR | clearly documented | implemented | TC-ERR-01 | corrupt outcome | stable code | corrupt_document, chunks 0 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | stderr sanitization opaque | PASS | baseline
F-161 | Typed chat errors | ERROR | clearly documented | implemented | TC-ERR-02 | 4 typed errors seen | codes+hints | invalid_scope/still_processing/no_evidence | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-162 | Refusal calibration codes | ERROR | clearly documented | implemented | TC-ERR-02 | evidence_missing class | per-class | category evidence_missing + hint | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Grep monitor usable | PASS | baseline
F-163 | Preview failure taxonomy | ERROR | clearly documented | implemented | TC-ERR-03 | bad token 404 | explicit 404 | 404 observed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Blank-frame rule SRC-only | PASS | baseline
F-164 | HTTP edge errors | ERROR | clearly documented | implemented | TC-ERR-04 | 401/403/404/409/422 | correct codes | all correct (matrix) | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | PG-503/Retry-After NT | PASS | baseline
F-165 | Storage/parser res errors | ERROR | clearly documented | implemented | TC-ERR-01 | quota/size/integrity | fences | dup-409; empty-422; no bypass seen | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | OOS/integrity untriggered | PASS | baseline
F-166 | At-rest/in-transit model | SEC | clearly documented | implemented | TC-SEC-06 | roundtrip + UUID keys | opaque store | byte-identical; UUID object IDs | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | TLS out of scope | PASS | baseline
F-167 | Tenant filter + gates | SEC | clearly documented | implemented | TC-SEC-03 | own-files-only | isolated | only own 7 files ever visible | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Cross-tenant negative NT | PASS | baseline
F-168 | Preview hardening | SEC | clearly documented | implemented | TC-SEC-07 | token+expiry | short-lived | 899s token; peer-bind default | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | CSP/sandbox SRC-only | PASS | baseline
F-169 | Session/token hardening | SEC | clearly documented | implemented | TC-AUTH-02 | rotation+revoke | changed pw kills sessions | chpass revoked old session | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-170 | Capability hardening | SEC | clearly documented | implemented | TC-SEC-08 | scoped runs | no widening | scope enforced live | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | TTL math conflict -> drift | PASS | baseline
F-171 | Untrusted-input doctrine | SEC | clearly documented | implemented | TC-SEC-05 | no prompt injectifacts | clean | no doc text in answers verbatim-abuse | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Adversarial fuzz out of scope | PASS | baseline
F-172 | Secrets doctrine | SEC | clearly documented | implemented | TC-OPS-01 | zero literals; flats | compose clean | no secret in compose/example | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Rotation untested live | PASS | baseline
F-173 | Residual-risk disclosures | SEC | clearly documented | accurate | TC-SEC-09 | topology matches | as documented | single-Uvicorn, agent-tools, proxy-peer | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Docs honest | PASS | baseline
F-174 | Web-search disclosure | SEC | clearly documented | implemented | TC-CHAT-06 | toggle semantics | user-gated | web only when ON | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-175 | Vuln reporting | SEC | clearly documented | process | - | email channel | no vuln found | none found | N/A |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No vulnerability to report | N/A | baseline
F-176 | Structured run logs | OBS | clearly documented | implemented | TC-OBS-01 | stage logs present | stage=8 etc | stage=8 + recall lines | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | qlog hash-only unverified | PASS | baseline
F-177 | Health/diagnostics | OBS | clearly documented | implemented | TC-OBS-02 | health + status routes | 200s | health 200; ai-status authoritative | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-178 | Release evidence artifacts | OBS | clearly documented | implemented | TC-OBS-03 | evidence dir | commands+payloads | /tmp/...-001 populated | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Manifest-gen out of scope | PASS | baseline
F-179 | Recovery scripts | OBS | clearly documented | implemented | - | scripts exist | present | repo present (not executed) | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Needs maintenance window | NOT TESTABLE | baseline
F-180 | Metrics/tracing | OBS | absent | absent | - | none documented | absent | absent | N/A |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Gap recorded | N/A | baseline
F-181 | Compose lifecycle | DEPLOY | clearly documented | implemented | TC-OPS-02 | live topology | external ollama | verified; no lavix-owned ollama | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-182 | Startup order+schema gate | DEPLOY | clearly documented | implemented | TC-OPS-05 | healthy boot | gated | all healthy; migrate svc exists | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Boot sequence historical | PASS | baseline
F-183 | Migrations discipline | DEPLOY | clearly documented | implemented | - | head version | v16 repo vs v12 docs | mismatch | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No migration run; drift filed | NOT TESTABLE | baseline
F-184 | First-admin bootstrap | DEPLOY | clearly documented | implemented | TC-AUTH-01 | registration path | works | self-registered (open) | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Trusted-window path docs-only | PASS | baseline
F-185 | Ollama standalone contract | DEPLOY | clearly documented | implemented | TC-OPS-03 | ext volume+tags | present | tags+endpoints verified | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Restart/persist operator-owned | PASS | baseline
F-186 | Recovery set+rehearsal | DEPLOY | clearly documented | implemented | - | capture+restore | tested set | not run | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Maintenance window needed | NOT TESTABLE | baseline
F-187 | Upgrade/rotation discipline | DEPLOY | clearly documented | implemented | - | procedures | documented | docs-level | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No upgrade in scope | NOT TESTABLE | baseline
F-188 | Promotion gate | DEPLOY | clearly documented | process | - | - | - | - | N/A |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No promotion in scope | N/A | baseline
F-189 | E2E harness | DEPLOY | clearly documented | implemented | TC-OPS-06 | smoke script passes | PASS | PASS chrome152 PDF.js ok | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Full harness not run live | PASS | baseline
F-190 | Web eval script | DEPLOY | clearly documented | implemented | - | script exists | present | repo present (not executed) | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Needs operator token+time | NOT TESTABLE | baseline
F-191 | Selection patience (test) | OTHER | clearly documented | implemented | TC-CHAT-16 | see F-055 | typed error | same evidence | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline
F-192 | Anon browser smoke | OTHER | clearly documented | implemented | TC-OPS-06 | run script CHROME_BIN | PASS | PASS + 9 assets | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Evidence in logs | PASS | baseline
F-193 | Authenticated acceptance | OTHER | clearly documented | implemented | - | harness needed | - | no harness in toolset | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Headless DOM only | BLOCKED | baseline
F-194 | Publish procedure | OTHER | clearly documented | process | - | - | - | - | N/A |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Out of scope | N/A | baseline
F-195 | Priority drill | OTHER | clearly documented | implemented | - | harness control | - | not run | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Needs E2E harness | NOT TESTABLE | baseline
F-196 | Ollama-only scope | OTHER | clearly documented | implemented | TC-CHAT-12 | no provider surface | ollama only | confirmed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Removed-vs-deferred -> drift | PASS | baseline

## API Tests
Method | Endpoint | Result | Verdict | Notes
PATCH | /api/files/rename/{file_id} | 200 rename + list shows name | PASS | new; conflict/perm/422 covered
DELETE | /api/files/delete/{id} | actionable 403 (grant path named) | PASS | policy unchanged
PUT | /api/ai/graph-memory (enable) | rev3 enabled | PASS | memory loop
GET | /api/ai/graph-memory/items | ACTIVE item provenanced | PASS | CRUD verified
PATCH/DELETE | /api/ai/graph-memory/items/{id} | edit 200, stale 409, delete 200 | PASS | lifecycle
DELETE | /api/ai/graph-memory + /personal-memory | 200 | PASS | vacuous (0 items)
GET | / | version 0.9.49-beta | PASS | bump served

## File-RAG Tests
Check | Result | Verdict
re-grant 305/306/307/310/311 -> ready 3/2/2/25/183 | all ready | PASS
deep-read totals exact words-figures | ground truth match | PASS
scoped single-file seller correct V1 | correct | PASS
combo total+tax exact | 7,799.00 + 1,189.68 | PASS
multi-file both flow (kept=6) | proven in logs | PASS
multi-file clean dual answer | model-limited, refused/speculated | PARTIALLY FIXED
revoke all 218 chunks removed (cleanup) | removed | PASS

## Memory Tests
Check | Result | Verdict
enable rev3; declaration ack 'try to save' | non-committal | PASS
worker accepted=1; ACTIVE I/name/QA provenanced | retained | PASS
new-chat recall 'Your name is QA.' (no Sources) | personalization | PASS
About Me 'Your name is QA.' | deterministic | PASS
edit 200 / stale 409 / delete 200 / total 0 | lifecycle | PASS
1.0 confidence, 90-day expiry, revision 1 | bands | PASS
disable rev6 (cleanup) | off | PASS

## Security Tests
Check | Result | Verdict
actionable delete 403 (no auto-grant) | denial + path | PASS
rename gated perm_rename (403 covered in unit) | gate | PASS
memory tenant isolation (own items only) | isolated | PASS
no secrets touched; corpus untouched | clean | PASS

## Error Tests
Check | Result | Verdict
clock 'right now' answers (was refused) | IST answer | PASS
instruction 'SWITCHED' exact (was refused x2) | exact | PASS
strict refusal replaces phantom 97,799 | error card path | PASS
paired name-numbers no longer refuse (Vision 2030) | unit + live | PASS
rename 404/409/422 matrix | all correct | PASS

## Execution Logs
Time (UTC) | Action | Result
00:05 | images built 0.9.49-beta (api/agent/worker/webui) | built
00:10 | services recreated + healthy | all 0.9.49-beta
00:12 | rename 200 + actionable 403 + version live | verified
00:15 | clock + SWITCHED answer live | verified
00:20 | memory enabled; declaration acked | ack
00:28 | worker accepted=1; ACTIVE item | FIXED 001
00:30 | recall + About Me correct | verified
00:32 | multi-file probes; fairness flows; paired guard improved | partial 003
00:38 | strict refusal fired on phantom 97,799 | mechanism live
00:40 | deep-read exact; combo exact | FIXED 004/005
00:45 | 306 re-ingest drained invoice/model | FIXED 007
00:50 | edit/409/delete/clears; lifecycle green | verified
00:55 | suites: 290 targeted + 497 cuga + 1117 unit + webui 87/2 | green
01:10 | cleanup: 218 chunks revoked, chats deleted, memory off, folder trashed | clean

## Documentation Drift
Item | Baseline status | Post-fix status
rename route | documented-missing | IMPLEMENTED + documented (code matches docs)
bulk grant/revoke, scope, topics, clear-embeddings, live/ready | implemented-undocumented | unchanged (docs TODO)
auth/settings, files/search, chat/revoke | documented-missing | unchanged (still 404; out of scope)
Neo4j projection conflict | conflict | live: projection_state=projected observed; conflict remains
timeout math conflict | conflict | unchanged
version strings | conflict | RESOLVED (0.9.49-beta everywhere executable)
perm_delete default | gap | DOCUMENTED (api.md + security.md)
About Me shape | conflict | live: single summary paragraph observed

## Coverage
Category | Total | Pass/Fixed | Partial | Blocked/NT/NA/KL | Coverage%
APP/CORE | 8 | 7 | 0 | 1 | 87.5%
UI | 37 | 31 | 0 | 6 | 83.8%
CHAT | 15 | 15 | 0 | 0 | 100.0%
MODELS | 14 | 11 | 0 | 3 | 78.6%
FILES | 19 | 19 | 0 | 0 | 100.0%
RAG | 12 | 10 | 1 | 1 | 91.7%
MEMORY | 18 | 16 | 0 | 2 | 88.9%
CONV | 6 | 5 | 0 | 1 | 83.3%
AUTH | 10 | 8 | 0 | 2 | 80.0%
ADMIN | 6 | 4 | 0 | 2 | 66.7%
API | 8 | 8 | 0 | 0 | 100.0%
INFRA | 6 | 6 | 0 | 0 | 100.0%
ERROR | 6 | 6 | 0 | 0 | 100.0%
SEC | 10 | 9 | 0 | 1 | 90.0%
OBS | 5 | 3 | 0 | 2 | 60.0%
DEPLOY | 10 | 5 | 0 | 5 | 50.0%
OTHER | 6 | 3 | 0 | 3 | 50.0%