## Executive Summary
Item | Detail
Run ID | LAVIX-QA-RELEASE-20260926-002
Window (UTC) | 2026-09-26T10:07Z..10:55Z (UTC)
Scope | release-condition cleanup only; no feature refactors
BLOCKED | 8 → 8 (all reclassified, none testable without harness/grant)
NOT TESTABLE | 15 → 15 (all environment/product/limitation)
N/A | 5 → 5 (confirmed correct)
Fixed | 0 (no implementation defects found; reranker = tag-only rebuild)
E2E | NOT TESTABLE (retained; isolated harness not run)
Reranker | CLEARED (rebuilt c19cf268ab40, healthy, live rerank 200 OK)
Git tree | REVIEWED DIRTY (45 paths classified, manifest below; no commit)
New defects | 0
Final verdict | CONDITIONAL GO (shorter condition list; see Release Conditions)

## Release Conditions
Item | Was | Investigation | Disposition | Result
F-016 chips/arrows | BLOCKED | no auth browser harness; smoke render only | ENVIRONMENT REQUIRED | retain BLOCKED
F-025 thumbnail regen | BLOCKED | backend preview verified; button needs browser | ENVIRONMENT REQUIRED | retain BLOCKED
F-041 ODL status view | BLOCKED | admin-only; 403 verified | PRODUCT DECISION REQUIRED (admin grant) | retain BLOCKED
F-044 responsive/kbd/a11y | BLOCKED | no interactive browser | ENVIRONMENT REQUIRED | retain BLOCKED
F-137/140/141 admin APIs | BLOCKED x3 | 403s verified; no admin creds | PRODUCT DECISION REQUIRED | retain BLOCKED
F-064 revision 409 | BLOCKED | admin-write path | PRODUCT DECISION REQUIRED | retain BLOCKED
F-193 auth acceptance | BLOCKED | headless DOM only | ENVIRONMENT REQUIRED | retain BLOCKED
F-011/132 idle 120m | NOT TESTABLE | 7200s config verified; sit impractical | ACCEPTED LIMITATION | retain
F-033 vendor-failure card | NOT TESTABLE | vendors healthy 4h; honest-card path covered | ACCEPTED LIMITATION | retain
F-070 rerank fail-open | NOT TESTABLE | no fault injection on live | ACCEPTED (fail-open code path unit-covered) | retain
F-103 backfill CLI | NOT TESTABLE | live inference load risk | ENVIRONMENT (maintenance window) | retain
F-121 topics flag-off | NOT TESTABLE | flag off by design | ACCEPTED (isolation pinned) | retain
F-123 R1 scrub | NOT TESTABLE | white-box only | ACCEPTED | retain
F-128 stream races | NOT TESTABLE | no stream-control harness | ENVIRONMENT REQUIRED | retain
F-179/183/186/187 recovery+mig+upgrade | NOT TESTABLE x4 | windows out of scope | ENVIRONMENT REQUIRED | retain
F-190 web eval | NOT TESTABLE | operator token+time | ENVIRONMENT REQUIRED | retain
F-195 priority drill/E2E | NOT TESTABLE | isolated harness not run | ENVIRONMENT REQUIRED | retain E2E condition
N/A x5 (008/175/180/188/194) | N/A | process/gap/scope items, verified correct | — | retain N/A
F-074 model/vendor limits | KNOWN LIMITATION | docs-acknowledged quirks | ACCEPTED | retain
reranker tag | CONDITION | rebuilt, healthy, live 200 OK | CLEARED | condition removed
dirty tree (45 paths) | CONDITION | all intentional/test/docs/generated; manifest below | REVIEWED DIRTY | record, no commit
vendor flakiness | CONDITION | no flap in 4h; fail-open+honest cards verified | ACCEPTED | retain condition

## Blocked Features
Feature ID | Feature | Reason | Disposition
F-016 | Type chips + arrow scrollers | no auth browser harness | ENVIRONMENT REQUIRED
F-025 | Regenerate-thumbnail action | button needs browser (backend PASS) | ENVIRONMENT REQUIRED
F-041 | System status (ODL neutral) | admin-only view | PRODUCT DECISION REQUIRED
F-044 | Responsive/keyboard/a11y | no interactive browser | ENVIRONMENT REQUIRED
F-137 | Admin user/perm/policy | admin account required | PRODUCT DECISION REQUIRED
F-140 | Admin ai-models write | admin account required | PRODUCT DECISION REQUIRED
F-141 | Admin system/storage/users | admin account required | PRODUCT DECISION REQUIRED
F-193 | Authenticated acceptance | headless DOM only | ENVIRONMENT REQUIRED

## Not-Testable Features
Feature ID | Feature | Reason | Disposition
F-011 | 120-min idle lockout UX | impractical sit; 7200s verified | ACCEPTED LIMITATION
F-033 | No-relevant-web-sources card | no vendor failure; path covered | ACCEPTED LIMITATION
F-064 | Revisioned singleton (409) | admin-write path | PRODUCT DECISION REQUIRED
F-070 | Rerank fail-open | no live fault injection | ACCEPTED (unit-covered)
F-103 | Backfill CLI | live inference load | ENVIRONMENT (maintenance window)
F-121 | Question topics opt-OFF | flag off by design | ACCEPTED LIMITATION
F-123 | R1 secret scrub | white-box only | ACCEPTED LIMITATION
F-128 | Streaming race guards | no stream-control harness | ENVIRONMENT REQUIRED
F-132 | Idle contract 120m | impractical sit | ACCEPTED LIMITATION
F-179 | Recovery scripts | maintenance window | ENVIRONMENT REQUIRED
F-183 | Migrations discipline | no migration run | ENVIRONMENT REQUIRED
F-186 | Recovery set+rehearsal | maintenance window | ENVIRONMENT REQUIRED
F-187 | Upgrade/rotation discipline | out of scope | ENVIRONMENT REQUIRED
F-190 | Web eval script | operator token+time | ENVIRONMENT REQUIRED
F-195 | Priority drill / E2E | isolated harness not run | ENVIRONMENT REQUIRED

## NA Review
Feature ID | Feature | Why N/A | Still correct?
F-008 | Validation language | process note | yes
F-175 | Vuln reporting | no vuln found | yes
F-180 | Metrics/tracing | absent by design; gap recorded | yes
F-188 | Promotion gate | no promotion in scope | yes
F-194 | Publish procedure | out of scope | yes

## Git Change Manifest
File/group | Classification | Reason
agent_runtime/cuga_adapter.py, events.py, gateway.py | INTENTIONAL (BUG-003/004/005/006/009/010) | verified fixes + live proof
agent_runtime/main.py | INTENTIONAL (BUG-012) | version string
app/agent/retrieval.py | INTENTIONAL (BUG-003) | fairness quota
app/config.py, config.example.yml | INTENTIONAL (BUG-012) | version strings
app/graph_memory/ x4 | INTENTIONAL (BUG-001) | validation/worker/repo/service
app/ingestion/publisher.py, worker.py | INTENTIONAL (BUG-007) | enrich status + retry
app/routers/chat/orchestrator.py, schemas.py, tool_routes.py | INTENTIONAL (BUG-001/008 + deep-read removal) | notice logic, rename endpoint, route deletion
app/routers/files.py | INTENTIONAL (BUG-008/011) | rename endpoint + actionable 403
compose.yaml, compose.e2e.yaml | INTENTIONAL (BUG-012) | 0.9.49-beta tags
docs/api.md, architecture.md, security.md | DOCUMENTATION (drift fixes + policy + removal note) | verified wording
pyproject.toml, webui/package.json, App.jsx | INTENTIONAL (BUG-012) | version strings
webui vault-client.js | INTENTIONAL (BUG-008) | renameFile client
webui frontend-workflows.js/.test.mjs | INTENTIONAL (percentage floor) | floor logic + 8 asserts
tests/unit x6 modified + test_stack.py | TEST (coverage updates) | deliberate expectation updates + e2e scoped rewrite
uv.lock | GENERATED | version-bump fallout
8 new test files | TEST (new coverage) | 61+29 new tests
tests/qa-reports/ (untracked) | QA ARTIFACTS | 4 workbooks, intentional
UNRELATED/ACCIDENTAL | none found | full manifest reviewed

## Condition Resolution
Condition | Before | After | Evidence
reranker tag | 0.9.36-beta running | 0.9.49-beta rebuilt (c19cf268ab40), healthy, live rerank 200 OK | images + logs + scored search
E2E | NOT TESTABLE | NOT TESTABLE retained (harness requirements documented) | harness exists, not run
vendor flakiness | condition | no flap in window; safe paths verified | 4h logs + fail-open units
dirty tree | 36 files | 45 paths classified, 0 unrelated | manifest above
admin grants | 5 items blocked | still blocked; 403s verified | PRODUCT DECISION REQUIRED

## 196 Feature Matrix
Feature ID | Feature | Category | Documentation Status | Implementation Status | Test Case ID | Test Description | Expected Result | Actual Result | Verdict | Severity | Account | Environment | Model | Timestamp | Evidence Reference | Log Reference | Notes | Fix Verdict | Fix Evidence | Fix-002 Verdict | Release Verdict | Release-002 Disposition
F-001 | Encrypted vault, consent-separated indexing | APP/CORE | clearly documented | implemented | TC-APP-01 | Upload file, check state/index | not_granted, unindexed | 305/306/307 all not_granted pre-grant | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-002 | CUGA sole orchestrator | APP/CORE | clearly documented | implemented | TC-APP-02 | Chat calls traverse agent-runtime | agent stream 200, token deltas | httpx POST agent-runtime:8090 200 in api logs | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-003 | API as authority | APP/CORE | clearly documented | implemented | TC-APP-03 | Ownership/scope/admin gates | deny cross-tenant + non-admin admin | invalid_chat_scope; admin 403s | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-004 | Five-step runtime contract | APP/CORE | clearly documented | implemented | TC-APP-04 | Full upload->grant->ready->chat->sources cycle | end-to-end works | executed on 306/310 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-005 | Opt-in PG-authoritative memory | APP/CORE | clearly documented | implemented | TC-MEM-01 | Default OFF; PUT enable | enabled=false->true rev0->1 | verified live | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | See BUG-001/002 (extraction) | PASS | baseline | PASS | PASS | PASS
F-006 | One-authority discipline | APP/CORE | clearly documented | implemented | TC-APP-06 | Single Ollama, single orchestrator | no dup services | compose + runtime confirm | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-007 | Contract vocabulary | APP/CORE | clearly documented | implemented | TC-APP-07 | state/status duals; match% labels | consistent usage | ai-status duals; cards show % | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-008 | Validation language (must) | APP/CORE | clearly documented | process | - | - | - | - | N/A |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Process note, not executable | N/A | baseline | N/A | N/A | N/A
F-009 | Sign-in page | UI | clearly documented | implemented | TC-UI-01 | Register+login API; headless DOM render | 200 + auth DOM | user 34 created; DOM has Register/Username | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | evidence login-dom2.html | PASS | baseline | PASS | PASS | PASS
F-010 | Conditional Google button | UI | partially documented | implemented | TC-UI-02 | GET capabilities | google_oauth_enabled=false | false; no Google in DOM | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-011 | 120-min idle lockout UX | UI | clearly documented | implemented | TC-AUTH-06 | Config + endpoints | 7200s; activity-only extend | idle_timeout 7200; refresh/activity ok | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | 120-min wait impractical | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | NOT TESTABLE
F-012 | My Documents page | UI | clearly documented | implemented | TC-UI-03 | list + smoke render | files render | list 200; SPA renders | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | SRC+API | PASS | baseline | PASS | PASS | PASS
F-013 | Format label | UI | clearly documented | implemented | TC-UI-04 | list mime/format fields | application/pdf shown | mime_type present per file | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | SRC+API | PASS | baseline | PASS | PASS | PASS
F-014 | File-type label | UI | clearly documented | implemented | TC-UI-05 | doc_type values | controlled types | invoice/report/None observed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | 307 None -> BUG-007 | PASS | baseline | PASS | PASS | PASS
F-015 | Semantic tags + #tag exact | UI | clearly documented | implemented | TC-UI-06 | tags endpoint + grounding | grounded tags | 11 unique tags; invoice tags match PDF | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-016 | Type chips + arrow scrollers | UI | clearly documented | implemented | TC-UI-07 | Interactive chip scroll/geometry | 40px, no overlap/scrollbar | no interactive browser harness | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Needs authenticated browser | BLOCKED | baseline | BLOCKED | BLOCKED | BLOCKED
F-017 | Plain-text file search | UI | partially documented | implemented | TC-API-12 | POST /ai/search | ranked distinct files | 306 @73% + summary/tags/type | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-018 | File detail panel | UI | clearly documented | implemented | TC-UI-08 | ai-status detail fields | state/job/chunks/error | all fields returned | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | SRC+API | PASS | baseline | PASS | PASS | PASS
F-019 | Upload control (source only) | UI | clearly documented | implemented | TC-FILE-01 | Multipart uploads x4 | secured, not_granted | 305/306/307/310/311 ok | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-020 | Grant AI access | UI | clearly documented | implemented | TC-FILE-02 | Grant x5 + idempotency | queued jobs | all queued; keys accepted | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-021 | Cancel indexing (non-destr.) | UI | clearly documented | implemented | TC-FILE-06 | Grant then cancel 305 | cancelled, consent kept | cancelled; consent True | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-022 | Revoke AI access (destr.) | UI | clearly documented | implemented | TC-FILE-07 | Revoke 305..311 | chunks removed, not_granted | 3+2+2+25+183 removed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-023 | AI-state display incl. terminal | UI | clearly documented | implemented | TC-FILE-03 | Poll all test files | ready/failed/cancelled | ready x4, failed(corrupt_document), cancelled | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-024 | Tokenized preview (PDF.js) | UI | clearly documented | implemented | TC-FILE-10 | create-session + fetch | 200 PDF bytes | 899s token; 200 application/pdf 81KB | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-025 | Regenerate-thumbnail action | UI | clearly documented | target/not-shipped | TC-UI-09 | Header action + Try again | single action/status | no interactive browser | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Backend preview path PASS | BLOCKED | baseline | BLOCKED | BLOCKED | BLOCKED
F-026 | Viewer retry/download | UI | clearly documented | implemented | TC-FILE-11 | Download byte-compare; 404 paths | identical bytes | BYTE-IDENTICAL invoice.pdf | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | SRC+API | PASS | baseline | PASS | PASS | PASS
F-027 | Chat model selector | UI | clearly documented | implemented | TC-CHAT-02 | PUT chat-model switch x3 | active model changes | ministral->llama ok; bad->422 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-028 | Files toggle + @-menu + pill | UI | clearly documented | implemented | TC-CHAT-05 | Scope POST + file_ids + bad id | scope enforced | scope=[306] used; 999999->invalid_chat_scope | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | SRC+API | PASS | baseline | PASS | PASS | PASS
F-029 | Web toggle command | UI | clearly documented | implemented | TC-CHAT-06 | Web OFF refuse vs ON answer (PM India) | OFF refuse / ON 3 W-cards | observed exactly | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-030 | Streaming deltas, no leak | UI | clearly documented | implemented | TC-CHAT-01 | 15+ streamed answers scanned | only answer text | zero protocol leaks | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-031 | Source cards + match% | UI | clearly documented | implemented | TC-RAG-02 | Vault + web cards | grouped, 0-100 int | V1 49-55%; W1-3 89-100% | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-032 | Amber background banner | UI | clearly documented | implemented | TC-CHAT-09 | Conceptual Q web-off no files | unverified:true | photosynthesis unverified:true | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-033 | No-relevant-web-sources card | UI | clearly documented | implemented | TC-CHAT-10 | Force all-web-results-fail | card shown | vendors healthy all run | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No vendor failure observed | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | NOT TESTABLE
F-034 | Factual refusal | UI | clearly documented | implemented | TC-CHAT-08 | Inception director, web off | templated refusal | no_verifiable_evidence | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-035 | Follow-ups 0-2 bounded | UI | clearly documented | implemented | TC-CHAT-11 | Collect follow-ups across runs | <=64ch/10w topical | all runs 0-2, in bounds | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-036 | AI Models role map (ro) | UI | clearly documented | implemented | TC-SET-01 | model-config read; admin PUT 403 | read ok, write denied | 6 roles shown; PUT 403 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-037 | Safe Automatic + retention | UI | clearly documented | implemented | TC-MEM-02 | PUT enable 90; PUT 60 | rev1; 422 on 60 | verified | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | SRC+API | PASS | baseline | PASS | PASS | PASS
F-038 | About Me + copy | UI | clearly documented | implemented | TC-MEM-03 | GET graph-memory empty | empty summary | 'No relationship memories yet.' | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Copy btn SRC-only | PASS | baseline | PASS | PASS | PASS
F-039 | Memory items list/actions | UI | clearly documented | implemented | TC-MEM-04 | GET items; edit/approve/renew/del | list works | 200 empty; no items to act on | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Blocked by BUG-001 (0 items) | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-040 | Dual clear operations | UI | clearly documented | implemented | TC-MEM-05 | DELETE graph-memory + personal | cleared, files kept | no items to clear | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Blocked by BUG-001 | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-041 | System status (ODL neutral) | UI | clearly documented | implemented | TC-SET-02 | admin/system as non-admin | 403 (admin-only) | 403 verified | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Admin view untestable non-admin | BLOCKED | baseline | BLOCKED | BLOCKED | BLOCKED
F-042 | Clock override API-only | UI | clearly documented | implemented | TC-SET-03 | No Settings field; admin API | absent UI; API gated | consistent w/ docs | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-043 | Greeting handling | UI | partially documented | implemented | TC-CHAT-03 | hello | templated reply | 'Hello! How can I help you today?' | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-044 | Responsive/keyboard/a11y | UI | partially documented | implemented | TC-UI-10 | 800/390px, Enter, aria | targets/states | no interactive browser | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Smoke render only | BLOCKED | baseline | BLOCKED | BLOCKED | BLOCKED
F-045 | Troubleshooting surfaces | UI | clearly documented | implemented | TC-UI-11 | Match hints to observations | hints accurate | hint text matched refusal states | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Docs check | PASS | baseline | PASS | PASS | PASS
F-046 | Ollama-only, no override | CHAT | clearly documented | implemented | TC-CHAT-12 | provider=openrouter | 422 | 422 observed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | openrouter_models:[] | PASS | baseline | PASS | PASS | PASS
F-047 | Bounded history + run UUID | CHAT | clearly documented | implemented | TC-CHAT-13 | Durable chat history | user msg persisted | user msg in GET chat | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-048 | 300s HMAC capability | CHAT | clearly documented | implemented | TC-CHAT-14 | Scope enforcement | intersect, never widen | invalid_chat_scope on 999999 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | TTL math -> drift C-3 | PASS | baseline | PASS | PASS | PASS
F-049 | SSE public contract | CHAT | clearly documented | implemented | TC-CHAT-01 | token/sources/followups/[DONE] | exact shape | {type:token/content} etc. | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-050 | Parametric block 3-class | CHAT | clearly documented | implemented | TC-CHAT-08/09 | refuse/label/exempt | all three seen | refuse+unverified+calc/clock/greet | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-010 edge noted | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-051 | Toggle forces prefetch | CHAT | clearly documented | implemented | TC-CHAT-06 | Web ON factual | answered w/ cards | PM India answered | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-052 | Bounded tool set | CHAT | clearly documented | implemented | TC-CHAT-15 | vault/web/calc/clock/recall | each fires | all fired; recall 200s in logs | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-053 | Chat clock IST | CHAT | clearly documented | implemented | TC-CHAT-04 | time phrasings | +05:30 answer | 2 documented phrasings ok | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-006 variant noted | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-054 | Calculator exact format | CHAT | clearly documented | implemented | TC-CHAT-04 | 137*5+60 | 745 | 'The result is 745.' 3 deltas | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-055 | file_still_processing wait | CHAT | clearly documented | implemented | TC-CHAT-16 | Chat processing file 311 | typed error | file_still_processing + hint | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-056 | Image-chat rejected | CHAT | clearly documented | implemented | TC-CHAT-17 | POST images payload | 422 | 'Image chat is not enabled' | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-057 | Deep-read single file | CHAT | partially documented | implemented | TC-CHAT-18 | deep-read 306 totals | grounded numbers | 97,799 vs truth 7,799 | FAIL | P2 | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-004 | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-058 | Sticky scope + killswitch | CHAT | clearly documented | implemented | TC-CHAT-19 | scope=[306], ask w/o file_ids | uses scope | Clicktech answer from scope | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-059 | Usage counts persisted | CHAT | clearly documented | implemented | TC-CHAT-20 | usage event present | prompt/completion counts | not captured by parser | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Parser gap; stats show durable msgs | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-060 | Memory never evidence | CHAT | clearly documented | implemented | TC-MEM-06 | Sources during memory chats | no memory cards | zero memory Sources seen | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-061 | Six model roles | MODELS | clearly documented | implemented | TC-SET-01 | model-config roles | chat/vision/intel/memory/embed/rerank | all present | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-062 | Role defaults | MODELS | clearly documented | implemented | TC-SET-04 | default tags | llama3b/snowflake/qwen2.5vl | match live config | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-063 | Allowlist + ceiling | MODELS | clearly documented | implemented | TC-CHAT-02 | bad model rejected | 422 | 422 nonexistent-model:999 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-064 | Revisioned singleton (409) | MODELS | clearly documented | implemented | TC-SET-05 | stale expected_revision | 409 | admin-only; untestable | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Non-admin account | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | NOT TESTABLE
F-065 | Read-only embed/reranker | MODELS | clearly documented | implemented | TC-SET-04 | roles read-only in UI contract | observed flags | embedding dim + reranker model fixed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Config-level | PASS | baseline | PASS | PASS | PASS
F-066 | Availability probing | MODELS | partially documented | implemented | TC-SET-01 | available/configured flags | per-role flags | 8 Ollama tags listed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-067 | 16K ctx + placement policy | MODELS | clearly documented | implemented | TC-MOD-01 | ctx/placement evidence | 16k chat; cpu bg | 1024-d embeddings flow; ollama ps untested | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | ollama ps NOT TESTABLE live | PASS | baseline | PASS | PASS | PASS
F-068 | Single synthesis invocation | MODELS | clearly documented | implemented | TC-CHAT-01 | one answer stream per req | monotonic deltas | observed all runs | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-069 | Streaming provenance gate | MODELS | clearly documented | implemented | TC-CHAT-01 | no code/tool/log leak | clean answers | 15+ answers clean | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-070 | Rerank fail-open | MODELS | clearly documented | implemented | TC-RAG-03 | kill reranker mid-query | hybrid order kept | reranker healthy; kill unsafe live | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Would disrupt live stack | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | reranker cleared; others unchanged (NOT TESTABLE)
F-071 | Worker-only bounds+fallback | MODELS | clearly documented | implemented | TC-RAG-04 | intel produced; vision n/a | model intel 3 files | invoice/report/qatar model intel | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Vision fallback not triggered | PASS | baseline | PASS | PASS | PASS
F-072 | Big-model ops path | MODELS | clearly documented | implemented | TC-MOD-02 | allowlist has 12B/20B-class | ministral/gemma listed | 6-model allowlist live | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Pull/restart procedural | PASS | baseline | PASS | PASS | PASS
F-073 | Never pulls/unloads | MODELS | clearly documented | implemented | TC-MOD-03 | Ollama external untouched | no lavix-owned volume ops | external lavix-ollama net | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-074 | Small-model/vendor limits | MODELS | partially documented | known limits | TC-MOD-04 | observe quirks | quirks logged | word-number totals; vendor healthy | KNOWN LIMITATION |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Docs acknowledge | KNOWN LIMITATION | baseline | KNOWN LIMITATION | KNOWN LIMITATION | KNOWN LIMITATION
F-075 | Multipart upload checks | FILES | clearly documented | implemented | TC-FILE-01 | uploads + dup + empty | secured/409/422 | 409 dup w/ existing_id; 422 empty | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-076 | AES/RSA/UUID/SHA storage | FILES | clearly documented | implemented | TC-FILE-10 | download byte-compare | identical | BYTE-IDENTICAL 81KB | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | crypto internals opaque | PASS | baseline | PASS | PASS | PASS
F-077 | MIME-first routing + CSV exc. | FILES | clearly documented | implemented | TC-FILE-04 | corrupt .pdf sniff | octet-stream wins | random bytes -> octet-stream | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | CSV variant untested (no sample) | PASS | baseline | PASS | PASS | PASS
F-078 | Supported format matrix | FILES | clearly documented | implemented | TC-FILE-05 | PDF path live | ready+chunks | 4 PDFs ready (3/2/2/25 ch) | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Non-PDF rows BLOCKED: corpus 29/29 PDF | PASS | baseline | PASS | PASS | PASS
F-079 | Unsupported handling | FILES | clearly documented | implemented | TC-FILE-04 | corrupt/empty/octet grant | failed/422/415-path | corrupt_document terminal | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Audio/video samples absent | PASS | baseline | PASS | PASS | PASS
F-080 | Terminal vs retryable | FILES | clearly documented | implemented | TC-FILE-04 | corrupt grant outcome | terminal, no OCR loop | failed corrupt_document | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-081 | Rename display-only | FILES | clearly documented | missing | TC-API-13 | PATCH /files/rename/305 | renamed | 404 | FAIL | P2 | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-008; folders PUT works | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-082 | Exact state machine+compat | FILES | clearly documented | implemented | TC-FILE-03 | state+status duals | both vocabularies | state + status returned | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-083 | Replacement-safe publish | FILES | clearly documented | implemented | TC-FILE-08 | revoke->regrant rev2,rev3 | new revisions queue | rev 2,3 observed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Replacement-while-ready NT | PASS | baseline | PASS | PASS | PASS
F-084 | Grant idempotency/bulk | FILES | clearly documented | implemented | TC-FILE-02 | Idempotency-Key reuse | same desired rev | keys accepted; bulk routes untested | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Bulk endpoints not exercised | PASS | baseline | PASS | PASS | PASS
F-085 | Worker claim/lease/beat | FILES | clearly documented | implemented | TC-FILE-03 | jobs drain on live workers | claimed+published | 13 jobs drained across run | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Inferred from outcomes | PASS | baseline | PASS | PASS | PASS
F-086 | Per-transition fences | FILES | clearly documented | implemented | TC-SEC-03 | ownership/consent/lease | deny + preserve | scope/perm denials; consent fences | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-087 | File/folder lifecycle | FILES | clearly documented | implemented | TC-FILE-09 | move/copy/trash/restore | ops work | move+copy ok; file-trash 403 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | File trash BLOCKED: perm (BUG-011) | PASS | baseline | PASS | PASS | PASS
F-088 | disable-all alias | FILES | clearly documented | implemented | TC-FILE-06 | POST disable-all-embeddings | deprecated+preserve | deprecated:true + replacement | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-089 | AI-status polling | FILES | clearly documented | implemented | TC-FILE-03 | poll 6 files | state/chunks/error | all fields incl. error_code | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-090 | Stats honest denominator | FILES | clearly documented | implemented | TC-API-14 | GET /ai/stats | indexable vs supported | indexable:4/searchable:4/failed:1 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-091 | files vs content search | FILES | clearly documented | implemented | TC-API-12 | POST /ai/search | distinct-file ranking | 306 @73% count=1 total_files=3 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | /files/search 404 -> drift | PASS | baseline | PASS | PASS | PASS
F-092 | Bearer download | FILES | clearly documented | implemented | TC-FILE-11 | GET download/306 | bytes | 81KB identical | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-093 | Uppercase .PDF discovery | FILES | partially documented | implemented | TC-FILE-05 | QA-001-QATAR.PDF ingest | application/pdf ready | ready 25 chunks, tags | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-094 | Canonical doc + provenance | RAG | clearly documented | implemented | TC-RAG-01 | answers cite file evidence | grounded spans | order/invoice nos exact | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Page locators not surfaced | PASS | baseline | PASS | PASS | PASS
F-095 | Boundary chunking+stable IDs | RAG | clearly documented | implemented | TC-RAG-01 | chunk counts published | non-empty chunk sets | 3/2/2/25/183 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | IDs opaque server-side | PASS | baseline | PASS | PASS | PASS
F-096 | Embeddings 1024/HNSW/GIN | RAG | clearly documented | implemented | TC-RAG-01 | retrieval functions | matches returned | 73%/49%/55% observed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | 1024-dim schema-level | PASS | baseline | PASS | PASS | PASS
F-097 | Hybrid + consent filter | RAG | clearly documented | implemented | TC-RAG-05 | revoked file excluded | 305 drops out | count 2->1, ids [307] | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-098 | Infinity rerank + floors | RAG | clearly documented | implemented | TC-RAG-06 | multi-file evidence | both files cited | 306 evidence missed | FAIL | P2 | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-003 | PARTIALLY FIXED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-099 | Public source shape | RAG | clearly documented | implemented | TC-RAG-02 | id/kind/%/file¦url | lean shape | exact shape both kinds | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-100 | Citation verify 0.5 | RAG | clearly documented | implemented | TC-RAG-07 | unverified notes appear | atoms checked | notes appear BUT wrong figs kept | FAIL | P2 | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-005 (verify gap) | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-101 | Doc intelligence/fields | RAG | clearly documented | implemented | TC-RAG-08 | type/summary/tags x4 | model intel | 3 model + 307 pending | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-007 linked | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-102 | Tag grounding rules | RAG | clearly documented | implemented | TC-RAG-08 | tags vs PDF text | grounded | amazon/gst/qatar/energy match | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-103 | Backfill CLI | RAG | clearly documented | implemented | - | dry-run --limit 5 | report only | not run (live GPU/model load) | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Would load live inference | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | NOT TESTABLE
F-104 | Web fan-out + guards | RAG | clearly documented | implemented | TC-RAG-09 | Web ON entity Q | W-cards + rerank | bing/mwmbl URLs, 89-100% | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | SSRF internals opaque | PASS | baseline | PASS | PASS | PASS
F-105 | Retrieval-failure behavior | RAG | clearly documented | implemented | TC-RAG-10 | vague multi-file Q | typed refusal | 'None of tagged files...' | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-106 | Two memory stores | MEMORY | clearly documented | implemented | TC-MEM-01 | manual + graph routes | both respond | both 200 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-107 | Opt-in + AI permission | MEMORY | clearly documented | implemented | TC-MEM-02 | default off; enable | false->true | rev0->rev1 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-108 | Extraction boundary | MEMORY | clearly documented | implemented | TC-MEM-07 | secret-bearing prompt | no persist, no leak | refused; items still 0 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-109 | Subject->I + full excerpt | MEMORY | clearly documented | implemented | TC-MEM-04 | inspect stored item | subject I | 0 items to inspect | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Blocked by BUG-001 | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-110 | Confidence bands | MEMORY | clearly documented | implemented | TC-MEM-04 | active vs pending | bands applied | 0 items | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Blocked by BUG-001 | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-111 | Retention schedule | MEMORY | clearly documented | implemented | TC-MEM-02 | 90 set; 60 rejected | 422 on 60 | verified | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Expiry untestable (time) | PASS | baseline | PASS | PASS | PASS
F-112 | Lifecycle events | MEMORY | clearly documented | implemented | TC-MEM-04 | edit/approve/renew/del | each works | 0 items | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Blocked by BUG-001 | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-113 | Dual-consent repair | MEMORY | clearly documented | implemented | TC-MEM-08 | mismatch behavior | fail-closed + warning | no mismatch observed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Repair path untriggered | PASS | baseline | PASS | PASS | PASS
F-114 | Foreground-lease deferral | MEMORY | clearly documented | implemented | TC-MEM-09 | worker defers in chat | defer, no attempt burn | worker ran post-chat; lease keys n/a | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Contention drill NT (harness) | PASS | baseline | PASS | PASS | PASS
F-115 | Recall path kw->vec->graph | MEMORY | ambiguous | conflicted | TC-MEM-06 | recall returns items | bounded items | 0 items; recall 200s in logs | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Conflict C-1/C-2 unresolved | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-116 | Recall fail-closed | MEMORY | clearly documented | implemented | TC-MEM-06 | memory off + chat | chat works, no personal | verified | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-117 | About Me deterministic | MEMORY | partially documented | implemented | TC-MEM-03 | empty + shape | empty honest | 'No relationship memories yet.' | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Populated view untestable | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-118 | Memory routes CRUD | MEMORY | clearly documented | implemented | TC-MEM-02/03 | all graph routes | 2xx | GET/PUT/items 200 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Item-id routes untested (0 items) | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-119 | Saved Prefs 20x500 | MEMORY | clearly documented | implemented | TC-MEM-10 | POST/GET/DELETE pref | roundtrip | id1 saved, listed, deleted | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Dedupe/cap edges untested | PASS | baseline | PASS | PASS | PASS
F-120 | Neo4j projection opt-OFF | MEMORY | ambiguous | conflicted | TC-MEM-11 | projection evidence | rebuildable | startup constraints in logs; 0 items | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Conflict C-1; needs items | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-121 | Question topics opt-OFF | MEMORY | partially documented | implemented | TC-MEM-12 | GET topics | 200 empty | 200 | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Flag off; synthesis-use unobservable | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | NOT TESTABLE
F-122 | Recall-use directives | MEMORY | clearly documented | broken | TC-MEM-13 | declaration->ack->retain | items retained | acks BUT 0 items; 1 refusal | FAIL | P1 | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-001 + BUG-002 | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-123 | R1 secret scrub | MEMORY | partially documented | implemented | - | secret in rewrite | persist untouched | internals opaque | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | White-box only | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | NOT TESTABLE
F-124 | Same-call follow-ups | CONV | clearly documented | implemented | TC-CHAT-11 | no 2nd model call | instant with answer | all runs immediate | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Inferred | PASS | baseline | PASS | PASS | PASS
F-125 | Follow-up bounds | CONV | clearly documented | implemented | TC-CHAT-11 | 64ch/10w/topical | hold | all in bounds | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-126 | Omit + persist | CONV | clearly documented | implemented | TC-CHAT-11 | empty allowed | no filler | [] seen (greeting/calc) | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | content_json opaque | PASS | baseline | PASS | PASS | PASS
F-127 | Durable chats equal | CONV | clearly documented | implemented | TC-CHAT-13 | GET chat messages | user persisted | user msg persisted; stats durable=1 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Assistant byte-equality inferred | PASS | baseline | PASS | PASS | PASS
F-128 | Streaming race guards | CONV | clearly documented | implemented | TC-CONV-01 | switch mid-stream | no cross-append | needs interactive control | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No stream-control harness | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | NOT TESTABLE
F-129 | No-rewind + envelope strip | CONV | clearly documented | implemented | TC-CHAT-01 | no wrapper leak | clean | no <LAVIX_ANSWER> fragments ever | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-130 | Registration gating | AUTH | clearly documented | implemented | TC-AUTH-01 | register xyris-test | 201 + uid | user_id 34 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Live registration_enabled=true | PASS | baseline | PASS | PASS | PASS
F-131 | Login/refresh/logout | AUTH | clearly documented | implemented | TC-AUTH-02 | rotation + logout kill | new pair; 401 after | rotation ok; post-logout 401 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-132 | Idle contract 120m | AUTH | clearly documented | implemented | TC-AUTH-06 | 7200s config | enforced | 7200 in login payload | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | 120-min wait impractical | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | NOT TESTABLE
F-133 | Sessions + 5-cap | AUTH | clearly documented | implemented | TC-AUTH-02 | list sessions | 1 active | 1 session row | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | 5-cap eviction untested | PASS | baseline | PASS | PASS | PASS
F-134 | Username/password rules | AUTH | clearly documented | implemented | TC-AUTH-03 | bad login 401 | 401 | 401 wrong pw | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Weak-pw register untested | PASS | baseline | PASS | PASS | PASS
F-135 | Google OAuth optional | AUTH | partially documented | implemented | TC-AUTH-04 | disabled flag | hidden flow | google_oauth_enabled=false | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Real OAuth out of scope | PASS | baseline | PASS | PASS | PASS
F-136 | Self-management routes | AUTH | partially documented | implemented | TC-AUTH-05 | persona/avatar/username/model | persona ok | persona updated | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Avatar/username PUTs untested | PASS | baseline | PASS | PASS | PASS
F-137 | Admin user/perm/policy | AUTH | partially documented | implemented | TC-SEC-01 | non-admin -> 403 | 403 all | 403 users/system/PUT | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Admin account required | BLOCKED | baseline | BLOCKED | BLOCKED | BLOCKED
F-138 | Permission flags | AUTH | clearly documented | implemented | TC-SEC-02 | upload/dl/AI ok; del deny | mixed per policy | 403 file delete; folder del ok | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | BUG-011 asymmetry | FIXED + VERIFIED | LAVIX-QA-FIX-20260926-001 | FIXED + VERIFIED | FIXED + VERIFIED | FIXED + VERIFIED
F-139 | Rate limit fail-closed | AUTH | clearly documented | implemented | TC-SEC-04 | config + abuse | throttle config | flag true per docs; no load test | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No load test on live | PASS | baseline | PASS | PASS | PASS
F-140 | Admin ai-models write | ADMIN | clearly documented | implemented | TC-SEC-01 | PUT as non-admin | 403 | 403 | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Admin account required | BLOCKED | baseline | BLOCKED | BLOCKED | BLOCKED
F-141 | Admin system/storage/users | ADMIN | partially documented | implemented | TC-SEC-01 | GET as non-admin | 403 | 403 | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Admin account required | BLOCKED | baseline | BLOCKED | BLOCKED | BLOCKED
F-142 | Single-file config | ADMIN | clearly documented | implemented | TC-OPS-01 | config.yml live; no .env | resolution works | live registration_enabled=true read | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Secrets never printed | PASS | baseline | PASS | PASS | PASS
F-143 | Config key inventory | ADMIN | clearly documented | implemented | TC-OPS-01 | example.yml groups | all groups | 14 groups inventoried | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Docs-level | PASS | baseline | PASS | PASS | PASS
F-144 | Bootstrap script | ADMIN | clearly documented | implemented | - | script exists | generates config+keys | repo present (not executed) | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Not executed on live | PASS | baseline | PASS | PASS | PASS
F-145 | Missing-config refusal | ADMIN | clearly documented | implemented | - | startup gate | fail-closed | healthy boot implies present | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Negative test N/A live | PASS | baseline | PASS | PASS | PASS
F-146 | Version/discovery/health | API | clearly documented | implemented | TC-API-01 | /, /api, health, openapi | 200 + 84 paths | all 200; 84 paths | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-147 | Curl upload-to-chat flow | API | clearly documented | implemented | TC-E2E-01 | docs workflow verbatim | works | executed end-to-end | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-148 | Route inventory | API | clearly documented | implemented | TC-API-02 | openapi enumeration | match docs +/- drift | 84 paths; 9 drift items | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Drift sheet filed | PASS | baseline | PASS | PASS | PASS
F-149 | File-scope validation | API | clearly documented | implemented | TC-CHAT-16 | bad/oversize scope | typed/422 | invalid_chat_scope; 422 x51 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-150 | Public projection | API | clearly documented | implemented | TC-CHAT-01 | leak scan | clean | 15+ answers clean | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-151 | Credential refusal-wins | API | clearly documented | implemented | TC-SEC-05 | sk-live+password prompt | no value anywhere | refused; zero secret echo | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | qlog internals opaque | PASS | baseline | PASS | PASS | PASS
F-152 | Compat + error envelope | API | clearly documented | implemented | TC-API-03 | dual fields; err shape | stable | state/status duals; {error,code} | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-153 | Private agent APIs | API | clearly documented | implemented | TC-API-04 | recall-graph in logs | 200 internal | 8x recall-graph 200 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No capability to call directly | PASS | baseline | PASS | PASS | PASS
F-154 | Service graph | INFRA | clearly documented | implemented | TC-OPS-02 | compose ps all healthy | 13 up | 13 running healthy | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-155 | Split images | INFRA | clearly documented | implemented | TC-OPS-02 | image IDs pinned | distinct IDs | 5 lavix IDs recorded | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Dockerfile-level static | PASS | baseline | PASS | PASS | PASS
F-156 | Networks + Ollama ext | INFRA | clearly documented | implemented | TC-OPS-03 | external ollama reachable | tags listed | 8 tags via 127.0.0.1:11435 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | agent-tools firewall note | PASS | baseline | PASS | PASS | PASS
F-157 | Durable tables | INFRA | clearly documented | implemented | TC-OPS-04 | persistence observed | chats/files/jobs | chat+files+jobs roundtrips | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No direct SQL (policy) | PASS | baseline | PASS | PASS | PASS
F-158 | Single API replica | INFRA | clearly documented | implemented | TC-OPS-02 | one api container | 1 replica | 1 lavix-api | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Config-level | PASS | baseline | PASS | PASS | PASS
F-159 | Resource bounds+mounts | INFRA | clearly documented | implemented | TC-OPS-02 | healthy under load | no OOM | 33% mem free; 1.2MB ingested | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Limits static | PASS | baseline | PASS | PASS | PASS
F-160 | process_failed diag | ERROR | clearly documented | implemented | TC-ERR-01 | corrupt outcome | stable code | corrupt_document, chunks 0 | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | stderr sanitization opaque | PASS | baseline | PASS | PASS | PASS
F-161 | Typed chat errors | ERROR | clearly documented | implemented | TC-ERR-02 | 4 typed errors seen | codes+hints | invalid_scope/still_processing/no_evidence | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-162 | Refusal calibration codes | ERROR | clearly documented | implemented | TC-ERR-02 | evidence_missing class | per-class | category evidence_missing + hint | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Grep monitor usable | PASS | baseline | PASS | PASS | PASS
F-163 | Preview failure taxonomy | ERROR | clearly documented | implemented | TC-ERR-03 | bad token 404 | explicit 404 | 404 observed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Blank-frame rule SRC-only | PASS | baseline | PASS | PASS | PASS
F-164 | HTTP edge errors | ERROR | clearly documented | implemented | TC-ERR-04 | 401/403/404/409/422 | correct codes | all correct (matrix) | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | PG-503/Retry-After NT | PASS | baseline | PASS | PASS | PASS
F-165 | Storage/parser res errors | ERROR | clearly documented | implemented | TC-ERR-01 | quota/size/integrity | fences | dup-409; empty-422; no bypass seen | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | OOS/integrity untriggered | PASS | baseline | PASS | PASS | PASS
F-166 | At-rest/in-transit model | SEC | clearly documented | implemented | TC-SEC-06 | roundtrip + UUID keys | opaque store | byte-identical; UUID object IDs | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | TLS out of scope | PASS | baseline | PASS | PASS | PASS
F-167 | Tenant filter + gates | SEC | clearly documented | implemented | TC-SEC-03 | own-files-only | isolated | only own 7 files ever visible | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Cross-tenant negative NT | PASS | baseline | PASS | PASS | PASS
F-168 | Preview hardening | SEC | clearly documented | implemented | TC-SEC-07 | token+expiry | short-lived | 899s token; peer-bind default | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | CSP/sandbox SRC-only | PASS | baseline | PASS | PASS | PASS
F-169 | Session/token hardening | SEC | clearly documented | implemented | TC-AUTH-02 | rotation+revoke | changed pw kills sessions | chpass revoked old session | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-170 | Capability hardening | SEC | clearly documented | implemented | TC-SEC-08 | scoped runs | no widening | scope enforced live | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | TTL math conflict -> drift | PASS | baseline | PASS | PASS | PASS
F-171 | Untrusted-input doctrine | SEC | clearly documented | implemented | TC-SEC-05 | no prompt injectifacts | clean | no doc text in answers verbatim-abuse | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Adversarial fuzz out of scope | PASS | baseline | PASS | PASS | PASS
F-172 | Secrets doctrine | SEC | clearly documented | implemented | TC-OPS-01 | zero literals; flats | compose clean | no secret in compose/example | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Rotation untested live | PASS | baseline | PASS | PASS | PASS
F-173 | Residual-risk disclosures | SEC | clearly documented | accurate | TC-SEC-09 | topology matches | as documented | single-Uvicorn, agent-tools, proxy-peer | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Docs honest | PASS | baseline | PASS | PASS | PASS
F-174 | Web-search disclosure | SEC | clearly documented | implemented | TC-CHAT-06 | toggle semantics | user-gated | web only when ON | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-175 | Vuln reporting | SEC | clearly documented | process | - | email channel | no vuln found | none found | N/A |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No vulnerability to report | N/A | baseline | N/A | N/A | N/A
F-176 | Structured run logs | OBS | clearly documented | implemented | TC-OBS-01 | stage logs present | stage=8 etc | stage=8 + recall lines | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | qlog hash-only unverified | PASS | baseline | PASS | PASS | PASS
F-177 | Health/diagnostics | OBS | clearly documented | implemented | TC-OBS-02 | health + status routes | 200s | health 200; ai-status authoritative | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-178 | Release evidence artifacts | OBS | clearly documented | implemented | TC-OBS-03 | evidence dir | commands+payloads | /tmp/...-001 populated | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Manifest-gen out of scope | PASS | baseline | PASS | PASS | PASS
F-179 | Recovery scripts | OBS | clearly documented | implemented | - | scripts exist | present | repo present (not executed) | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Needs maintenance window | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | NOT TESTABLE
F-180 | Metrics/tracing | OBS | absent | absent | - | none documented | absent | absent | N/A |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Gap recorded | N/A | baseline | N/A | N/A | N/A
F-181 | Compose lifecycle | DEPLOY | clearly documented | implemented | TC-OPS-02 | live topology | external ollama | verified; no lavix-owned ollama | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-182 | Startup order+schema gate | DEPLOY | clearly documented | implemented | TC-OPS-05 | healthy boot | gated | all healthy; migrate svc exists | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Boot sequence historical | PASS | baseline | PASS | PASS | PASS
F-183 | Migrations discipline | DEPLOY | clearly documented | implemented | - | head version | v16 repo vs v12 docs | mismatch | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No migration run; drift filed | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | NOT TESTABLE
F-184 | First-admin bootstrap | DEPLOY | clearly documented | implemented | TC-AUTH-01 | registration path | works | self-registered (open) | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Trusted-window path docs-only | PASS | baseline | PASS | PASS | PASS
F-185 | Ollama standalone contract | DEPLOY | clearly documented | implemented | TC-OPS-03 | ext volume+tags | present | tags+endpoints verified | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Restart/persist operator-owned | PASS | baseline | PASS | PASS | PASS
F-186 | Recovery set+rehearsal | DEPLOY | clearly documented | implemented | - | capture+restore | tested set | not run | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Maintenance window needed | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | NOT TESTABLE
F-187 | Upgrade/rotation discipline | DEPLOY | clearly documented | implemented | - | procedures | documented | docs-level | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No upgrade in scope | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | NOT TESTABLE
F-188 | Promotion gate | DEPLOY | clearly documented | process | - | - | - | - | N/A |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | No promotion in scope | N/A | baseline | N/A | N/A | N/A
F-189 | E2E harness | DEPLOY | clearly documented | implemented | TC-OPS-06 | smoke script passes | PASS | PASS chrome152 PDF.js ok | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Full harness not run live | PASS | baseline | PASS | PASS | PASS
F-190 | Web eval script | DEPLOY | clearly documented | implemented | - | script exists | present | repo present (not executed) | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Needs operator token+time | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | NOT TESTABLE
F-191 | Selection patience (test) | OTHER | clearly documented | implemented | TC-CHAT-16 | see F-055 | typed error | same evidence | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* |  | PASS | baseline | PASS | PASS | PASS
F-192 | Anon browser smoke | OTHER | clearly documented | implemented | TC-OPS-06 | run script CHROME_BIN | PASS | PASS + 9 assets | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Evidence in logs | PASS | baseline | PASS | PASS | PASS
F-193 | Authenticated acceptance | OTHER | clearly documented | implemented | - | harness needed | - | no harness in toolset | BLOCKED |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Headless DOM only | BLOCKED | baseline | BLOCKED | BLOCKED | BLOCKED
F-194 | Publish procedure | OTHER | clearly documented | process | - | - | - | - | N/A |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Out of scope | N/A | baseline | N/A | N/A | N/A
F-195 | Priority drill | OTHER | clearly documented | implemented | - | harness control | - | not run | NOT TESTABLE |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Needs E2E harness | NOT TESTABLE | baseline | NOT TESTABLE | NOT TESTABLE | NOT TESTABLE
F-196 | Ollama-only scope | OTHER | clearly documented | implemented | TC-CHAT-12 | no provider surface | ollama only | confirmed | PASS |  | xyris-test (id=34, non-admin) | live | llama3b-instruct-q6kl-16k:latest (+ministral-3:3b switch check) | 2026-09-25T20:36Z..2026-09-26T02:45Z (UTC) | /tmp/opencode/qa-LAVIX-QA-20260926-001 | docker lavix-* | Removed-vs-deferred -> drift | PASS | baseline | PASS | PASS | PASS

## Coverage
Metric | Value
Total | 196
PASS | 148
FIXED + VERIFIED | 19
BLOCKED | 8
NOT TESTABLE | 15
N/A | 5
KNOWN LIMITATION | 1
Tested (PASS+FIXED) | 167
Coverage % | 85.2%

## Reranker Verification
Check | Result
image rebuilt | c19cf268ab40 :0.9.49-beta
container | healthy
live rerank | POST /reranker:7997/rerank 200 OK
scored search | 338@82%
unit (61) | pass

## Regression Spot
Suite | Result
retrieval+fairness+discipline+attribution (61) | pass
ruff touched files | clean

## Evidence Index
Artifact | Location
prior workbooks | unchanged (06:17/06:20/14:15)
this workbook | LAVIX-QA-RELEASE-20260926-002.xlsx
tokens/logs | /tmp/opencode/qa-REL2-* (session only)